RKVY : Monitoring Visit to Goa

22 – 23 November 2010

R.N. Hegde

The monitoring visit to Goa was undertaken on 22-23 November 2010. A review meeting with all the representatives of implementing agencies of RKVY scheme was conducted on 22nd November 2010 at Panaji. The meeting was chaired by Shri. Ganesh Koyu, IAS, Secretary (Agriculture), Government of Goa. The names of the officials who attended the review meeting is furnished in the Annexure – I. The progress of each scheme was reviewed by the NIRD Monitoring Team. The Director Agriculture briefed on the present status of RKVY Scheme in Goa. The team expressed concern about the slow pace of implementation of RKVY Scheme in the State so also about non-preparation of C-DAP so far. During the meeting, emphasis was made for utilization of funds already received from the Government of India. The Department of Agriculture is the Nodal Department for RKVY in the State.

Present Status of Agriculture in Goa:

The total geographical area of the State of Goa is 3702 sq. kms (3, 70,200 ha) of which the net area sown during 2009-10 is 134,835 ha. About 31,423 ha are sown more than once. Out of the gross cropped area of 166258 ha, foodgrains occupy 60,029 ha (36.11%) horticultural crop 1, 01,173 ha (60.85%) and others like sugarcane and oilseeds occupy 5056 ha. (3.04%). The total irrigated area is about 37,924 ha (22.81%). The details are furnished in Table.1.

The 2001 population Census results indicate declining preference for agriculture activities in the State. In the year 1960-61, about 60 per cent of the workforce was engaged in agriculture which contributed 16.5 per cent to the State Domestic Product (SDP). However, successive decadal population Census results indicate a declining trend in workforce pursuing agriculture. The SDP estimates too indicate declining contribution from agriculture. The percentage of cultivators has declined from 16.6% in 1991 to 9.7% in 2001. There is also a corresponding decline in agricultural labourers from 10.9% to 6.9% during the same period. The contribution to the SDP has declined to below 8% at present.

The declining interest towards agriculture may be attributed to small land holdings, high cost of wages and non-availability of agriculture labourers. In addition to this, increasing urbanization has exerted pressure on land making the agriculture activity economically less viable on relative terms.

On the other hand Goa being a major tourist destination, there is tremendous scope for taking up of crops like fruits, flowers, medicinal plants, vegetables, etc. Considering these weaknesses and strengths, a number of measures have been initiated to revitalize the agriculture sector.

For the production and area coverage, various schemes and type of assistance are available at the door step of the farmer. The area coverage and production of major crops are given in Table 1. Paddy seed is the major item required by farmers which is arranged from National Seeds Corporation Ltd. and Karnataka State Seeds Corporation Ltd. Mini kits of different paddy varieties are provided to the farmers. The details of seed distributed in the last 3 years are given in Table 2.

Table: 1 The area coverage and production under major crops during last three years

| Sl. No. | Crop | 2006-07 | 2007-2008 | 2008-2009 |
| --- | --- | --- | --- | --- |
|  |  | Area in Ha | Production In tones | Area in Ha | Production in tonnes | Area in Ha | Production in tonnes |
| 1 | Paddy | Kharif | 35710 | 126830 | 34261 | 117208 | 34278 | 120206 |
| 2 |  | Rabi | 17275 | 66588 | 17930 | 65311 | 15688 | 56875 |
| 3 |  | TOTAL | 52985 | 193418 | 52191 | 182519 | 49966 | 177081 |
| 4 | Pulses | 12058 | 16250 | 11477 | 11261 | 9855 | 10141 |
| 5 | Groundnut | 2640 | 4600 | 3720 | 6998 | 3806 | 8208 |
| 6 | Vegetables | 8213 | 84290 | 5547 | 56027 | 5703 | 57603 |
| 7 | Sugarcane | 1120 | 58279 | 1034 | 56027 | 1021 | 49253 |
| 8 | Cashew | 55302 | 24380 | 55612 | 21942 | 55672 | 13165 |
| 9 | Coconut | 25468 | 126.68 Million nuts | 25545 | 127.57 Million nuts | 25608 | 128.18 Million nuts |

Table: 2  Seed assisted (Qty in MT) for the last four years

| Sl. No. | Year | Season | Total (Tonnes) |
| --- | --- | --- | --- |
|  |  | Kharif | Rabi |  |
| 1 | 2006-07 | 251.0 | 82.0 | 333.0 |
| 2 | 2007-08 | 265.0 | 88.0 | 353.0 |
| 3 | 2008-09 | 286.0 | 116.5 | 402.5 |
| 4 | 2009-10 | 330.0 | -- | 330.0 |

The State procures limited quantity of pulses of 10,140 MT and the availability of which is roughly about 845 MT per month. The State thus requires 2,155 M.T. of pulses per month which is made available from neighboring States by private traders.

The State produces about 40,000 tonnes of vegetables during Kharif season and 28,000-30,000 MT, of vegetables in Rabi season, as the rainfall during Kharif has been normal so far, the vegetable production has been secured. The average requirement of vegetables per month is about 13, 00 MT of which about 5,000 is locally produced and 8,000 MT are brought in from other States.

The State’s annual requirement is 6263 tonnes of fertilizers in terms of N (2237 tonnes), P (2177 tonnes), K (1849 tonnes). M/s Zuari Industries Ltd., is the lead fertilizer supplier. Fertilizers are arranged through Co-operative Societies as well as private traders; Use of Pesticide can be controlled by use of trichocards that release pest parasite. Fertilizer consumption in the State of Goa for last four years is given in Table3.

Table 3: Fertilizer Consumption in Goa

(Qty. in tones)

| Sl. No. | Year | N | P | K | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | 2006-07 | 2856 | 1430 | 1668 | 5954 |
| 2 | 2007-08 | 3472 | 1837 | 1820 | 7129 |
| 3 | 2008-09 | 3034 | 2912 | 2182 | 8128 |
| 4 | 2009-10 | 1464 | 1727 | 1022 | 4213 Till July 2009 |

During The Annual Plan 2010-11, the focus has remained on the development and rapid expansion of horticulture while trying to increase foodgrain production through increased productivity per unit area.

The status of fund allocation in the State Plan and how the Goa Government was ineligible to receive RKVY funds and now became eligible is furnished in Table 4.

Table 4: Goa State Plan Outlay and share of Agriculture

| Sl. No. | Year | Assistance to Agriculture and allied sector (Rs. Crore) | Total State Plan (Rs. Crore) | % Share to Agriculture and allied sector |
| --- | --- | --- | --- | --- |
| 1. | 2007-08 | 54.49 | 1430.00 | 3.81 |
| 2. | 2008-09 | 47.47 | 1737.00 | 2.73 |
| 3. | 2009-10 | 68.57 | 2058.00 | 3.33 |
| 4. | 2010-11 | 105.04 | 2449.00 | 4.29 |

A. State Level

- Financial Performance: The status of allocation, release and expenditure are given in Table 5. It can be observed that the State Government got an allocation of Rs. 226.54 lakhs under stream I & stream II, against which Rs. 170.00 lakhs was received by The Goa Government. During 2007-08, the eligibility criteria based on allocation to agriculture in the State Plan was not taken into account. Though allocation was made during 2008-09 and 2009-10, the release was not made as the State was declared as ineligible to receive RKVY funds. Out of Rs. 170.00 lakhs received in 2007-08 the State Government could utilize Rs.54.20 lakhs during 2008-09 and Rs. 20.03 lakhs during 2009-10. Total utilization of fund comes to only 16.38%. If we take only 2007-08 releases, the utilization comes to 43.66%. The project-wise allocations, releases and expenditure for the year 2008-09 is given in Table 6 and project- wise allocations, releases and expenditure for the year 2009-10 under Table 7. Agency-wise and year-wise releases and expenditure are given in Table 8.

Table: 5 Status of Allocation, Releases and Expenditure (as on 21.11.2010)

(Rs. in Lakhs)

| Year | GOI Total Allocation | Stream | GOI Total Releases | Expenditure | Unspent Balance | U.C. submitted | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2007-08 | 226.54 | I & II | 170.00 | -- | 170.00 | -- |  |
| 2008-09 | 691.00 |  | Nil | 54.20 (out of previous year) | 115.80 | 54.20 |  |
| 2009-10 | 1187.00 |  | Nil | 20.03 (out of 2007-08 release) | 95.77 | 20.03 |  |
| 2010-11 | 1133.00 | II | 283.00 | 0.00 | 283.00 | 0.00 |  |
| Total | 3237.54 |  | 453.00 | 74.23 | 378.77 | 74.23 |  |

N.B. Unspent balance -  Rs. 95.77+ 283.00= 378.77

Table 6: Project-wise Allocations, Releases and Expenditure during 2008-09

(as on 21.11.2010) (Rs in Lakhs)

| Sl. No | Name of the Project | Implementing Agencies | Total Project Cost | Total Releases | Total Expenditure |
| --- | --- | --- | --- | --- | --- |
| 1 | Processing facilities for Paddy | Sanjivani SSK ltd. | 75.00 | Nil | Nil |
| 2 | Promation of combines in Paddy | Directorate of Agriculture | 12.00 | Nil | Nil |
| 3 | Inventivising Paddy cultivation through SHG at village level- Setting up of Agro Services | Directorate of Agriculture | 31.20 | 15.27 | 15.27 |
| 4 | Asstt. For Raingun in Sugarcane | Directorate of Agriculture | 4.50 | Nil | Nil |
| 5 | Soil Health Improvement Assistance on purchase of Rock Phosphate | Directorate of Agriculture | 3.75 | 1.12 | 1.12 |
| 6 | Use of Organo-mineral chemical complex | Directorate of Agriculture | 16.80 | 16.80 | 16.80 |
| 7 | Satellite imaging & Data Generation | Directorate of Agriculture | 36 | 0.80 | 0.80 |
| 8 | HRD- Training of Farmers outside the State | Directorate of Agriculture | 0.80 | 0.69 | 0.69 |
| 9 | HRD- Training within the State | Directorate of Agriculture | 1.50 | 1.00 | 1.00 |
| 10 | HRD- Training of Fisherman for inland Fisheries | Department of Fisheries | 4.00 | 3.60 | 3.60 |
| a) | Upgradation of local live stock(Cows) | Directorate of Animal Husbandry and Veterinary Services | 5.00 | 3.16 | 3.16 |
| b) | Upgradation of local live stock(Cows) | Goa State Milk Producers Union | 13.90 | 13.90 | 10.45 |
|  | Administrative charges |  | 2.09 | 1.31 | 1.31 |
|  | C-DAP |  | 20.00 | 0.00 | 0.00 |
|  |  | Total | 226.54 | 57.65 | 54.20 |
|  |  | Balance with Goa Dairy |  | -3.45 |  |
|  |  | Grand Total |  | 54.20 | 54.20 |

Table 7: Project-wise Allocations, Releases and Expenditure during 2009-10

(Rs. in Lakhs)

| Sl. No | Name of the Project | Implementing Agencies | Total Project cost | Total releases | Total expenditure |
| --- | --- | --- | --- | --- | --- |
| 1 | Processing facilities for Paddy | Sanjivani SSK ltd. | 75.00 | Nil | Nil |
| 2 | Promation of combines in Paddy | Directorate of Agriculture | 6.00 | 6.00 | 6.00 |
| 3 | Inventivising Paddy cultivation through SHG at village level- Setting up of Agro Services | Directorate of Agriculture | 4.00 | 3.97 | 3.97 |
| 4 | Demonstration of Improved /Advanced Machinery | Directorate of Agriculture | 0.50 | 0.47 | 0.47 |
| 5 | HRD- Study tour of Farmes in inland Fisheries | Department of Fisheries | 1.30 | 1.01 | 1.01 |
| 6 | Development of Fodder Seed Nursery | Goa State Milk Producers Union | 3.00 | 3.00 | 3.00 |
| a) | Upgradation of local live stock(Cows & Bufallows) | Directorate of Animal Husbandry and Veterinary Services | 2.00 | 1.58 | 1.58 |
| b) | Upgradation of local live stock(Cows& Bufallows) | Goa State Milk Producers Union | 4.00 | 0.55 | 4.00 |
|  | C-DAP |  | 20.00 | 0.00 | 0.00 |
|  |  | Total | 115.80 | 16.58 | 20.03 |
|  |  | Balance of 08-09 with Goa Dairy |  | 3.45 | 0.00 |
|  |  | Grand Total |  | 20.03 | 20.03 |

Table 8: Agency-wise and Year-wise Releases and Expenditure

| Sl.No | Department/ Agencies | 2008-09 | 2009-10 | 2010-11 | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Releases | Expen diture | Releases | Expen diture | Releases | Expenditure | Releases | Expen diture |
| 1 | Directorate of Animal Husbandry & Veterinary Services | 3.16 | 3.16 | 1.58 | 1.58 | 0.00 | 0.00 | 4.74 | 4.74 |
| 2 | Directorate of Fisheries | 3.60 | 3.60 | 1.01 | 1.01 | 0.00 | 0.00 | 4.61 | 4.61 |
| 3 | Goa State Milk Producers Union | 13.90 | 10.45 | 3.55 | 7.00 | 0.00 | 0.00 | 17.45 | 17.45 |
| 4 | Directorate of Agriculture | 36.99 | 36.99 | 10.44 | 10.44 | 0.00 | 0.00 | 47.43 | 47.43 |
|  | Total | 57.65 | 54.20 | 16.58 | 20.03 | 0.00 | 0.00 | 74.23 | 74.23 |
|  | Balance released amount of 08-09 with Goa Milk Union | -3.45 | 0.00 | 3.45 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | Grand Total | 54.20 | 54.20 | 20.03 | 20.03 | 0.00 | 0.00 | 74.23 | 74.23 |

(as on 21.11.2010) (Rs. in lakhs)

It can be noted that at present only 4 agencies are implementing RKVY schemes viz., i) Department of Agriculture, ii) Department of Fisheries, iii) Department of Animal Husbandry and Veterinary Services and iv) Goa State Milk Producers Union. The reason for low utilization of funds is attributed two projects.

- Rs. 75.00 lakhs was allocated to M/s. Sanjivini Sugar Factory to install the rice mill. But, though the factory floated tenders twice no tenders were received. Hence, the project has still not taken off. During the review meeting, it was learnt that SLSC has set a time frame up to December 2010, failing which the mill will be allocated to Curtorim Service Co-operative Society.

- Rs. 20.00 lakhs was reserved for preparation of C-DAP. Here also the tenders received were over Rs. 20 lakhs and hence the State Government could not assign this task to anybody. However, it was suggested to float fresh tenders again so that the Goa Government can come out with C-DAP and SAP before March 2011, though there are only two districts in the State.

- The time lag in sanction and releases during 2008-09 and 2009-10 in Annexure – II. Not much time log has been observed between fund released by the State to the Nodal Agency and released to Implementing Agency.

- Since the C-DAP is not yet prepared, this issue of Projects submitted to SLSC coming from District Agriculture Plant (C-DAP)does not arise. It may be mentioned here that there are only two districts in Goa.

- Regarding the proportion of projects from SAP (not shown in C-DAP) submitted to SLSC is concerned, it is to inform that the C-DAP yet to be prepared

- It was observed that there is no dedicated team for RKVY at the Nodal Department to monitor RKVY Projects at the level of Nodal Agency. It was suggested to create a separate RKVY Cell at The Headquarters with proper staff and physical infrastructure to achieve the targets.

- There is no monitoring of any scheme by the Nodal Department.

- Convergence of RKVY schemes with other schemes was not noticed.

- As there is no separate RKVY Cell, State Level Meeting of all sector departments to review the progress of RKVY was not undertaken. There is an urgent need to create a dedicated RKVY Cell at the Nodal Agency to co-ordinate the RKVY schemes both at the state level and the district level.

- With regard to the number of innovative projects the Farm Mechanization Scheme through Farmers Club/SHG Movement could be considered as an innovative scheme under RKVY in the Goa State. Paddy combine, power tillers and weed cutter machines are granted to them giving 70% of the cost as a subsidy under the scheme, while 30% of the cost is borne by the Farmers Club. The Department of Agriculture was advised to submit a success story of this scheme. Shrinking of paddy land year after year due to industrialization and tourism development and non-availability of labour for paddy cultivation is a major drawback for agriculture growth in Goa. To overcome this problem, this scheme is ideal and becoming popular among the farmers.

- No specific District / Region Specific projects under RKVY are formulated. However, when C-DAP is prepared it may be kept in view.

- There are no projects of NAIP which can be scaled up with RKVY.

- The State Government proposes to take up the intervention of Watershed Development Project of RD Department under MGNREGA under their Watershed Development Scheme under stream – II in 2010-11, to which already funds have been released by GOI.

- Regarding the mechanism to screen the project proposals from all sectors before being but upto SLSC, at present the proposals received from line Departments are placed before SLSC directly as there is no Cell to scrutinize the projects.

There is a need to constitute a Project Screening Committee under the Chairmanship of Secretary, Agriculture Department where all the Heads of Departments / Implementing Agencies are the members to scrutinize the proposals before putting up to SLSC.

- Goa did not participate in the training programme on orientation training programme of RKVY Database and Information Management System (RDIMS) and on-line monitoring at NIRD, Hyderabad. Goa also was not represented in the review workshop held at Delhi during October 2010. There is no data entry with reference to 64 fields of data entry as required by MoA. The Government of Goa was advised to make contact with NIC and complete this task of submission of information under RDIMS at the earliest.

- Three SLSC, meetings were held on the dates mentioned below:

1st SLSC – 24.03.2008

2nd SLSC – 08.07.2009

3rd SLSC – 22.09.2010

District Level :

During the visit to the two districts in Goa, the following observations were made in respect of activities undertaken with RKVY funding.

- Upgradation of Local Livestock (cows & buffaloes) with artificial insemination.

Out of Rs. 7.00 lakhs released under this scheme, Rs. 4.78 lakhs has been utilized. A Veterinary Dispensary in Mandrem village Panchayat in Pernem taluk of North Goa district was visited. The Centre is getting semen of Jersey cows & Murrah buffaloes from Bangalore in liquid nitrogen containers which are used for artificial insemination. The Scheme consists of two phases. The first phase deals with the Artificial Insemination of local cows and buffaloes and the second phase is the confirmation of pregnancy and feeding incentives. During the visit it was understood that out of 67 insemination done on local cows, conception took place in 14 non-district cows resulting in the birth of 14 improved one. Visit was made to houses of some farmers also. The Scheme is being implemented successfully.

- Incentivising Paddy Cultivation through SHG at Village Level – Setting up of Agro Service Centres:

Out of Rs. 41.70 lakhs released Rs. 25.67 lakhs have been utilized. Under this Scheme, one paddy combine (for harvesting & threshing) and 10 Agro-Service Centres have been given which are managed by Self Help Groups of farmers.

Visit was made to Balaram Farmers Club in Priol village in Ponda taluk of South Goa district. This Club has 1100 members spread over 3 revenue villages under Cuncolien Panchayat. It is reported that out of 1100 members, 86 have been issued Kisan Credit Card from the UCO Bank, Mardol Branch. The Farmers Club takes up economic and cultural activities. The Club has been given VST Shakti Power Tillers @ Rs. 1.34 lakh per unit and weed cutter machines (@ Rs. 43 lakh per unit). The main crop in this area is arecanut. Farmers also take up high value vegetable crops like cucurbits, ridge gourd, bitter gourd and bottle gourd. Local banana which has high demand in local market is also cultivated. Regular monthly meetings are held in the local Shri Krishna Temple premises.

A visit was also made to Pedne Taluk Farmers Service Co-operative Society Limited, which provides services of input supply and facilitates marketing to farmers in the taluk. One Agro-service Centre has been established here. Two power tillers at a cost of Rs.1,32,330/- each and 10 spray pumps at a cost of Rs. 29,150/- each have been kept here for custom hiring by the farmers. The farmers are utilizing this service.

Weed cutter & power Tiller

Solar Power Cool Pushcart

General Observations:

The urbanization is in a very fast rate in Goa and how to maintain agriculture growth is a challenge for the Department of Agriculture. The value of vast area of land near the towns and cities are appreciated every year and the farmers wait to sell the land to builders / industries. The availability of agriculture labour is another problem.

Despite these facts, the Agriculture and allied Departments have prepared schemes for implementation under the RKVY. A scheme to be implemented by Goa State Horticulture Corporation (GSHC) needs special mention. It has designed a bicycle cart and solar powered cool pushcarts for marketing of fruits and vegetable in cities. During 2010-11, the GSHC proposes to fund on a pilot basis 20 carts for which SLSC has already approved. The cost of each push cool cart without bicycle comes to Rs. 68,000/-, while bicycle drawn cool cart costs Rs. 78,000/-.

Expected utilization during 2010-11:

The State Government hopes to utilize the unspent balance of Rs. 95.00 lakhs (Rs. 75.00 lakhs for rice mill and Rs. 20.00 lakhs for C-DAP). Further Rs. 283.00 lakhs under Stream – II is also expected to be utilized by releasing to Watershed Users Association, where the work has already been completed. The outlay of new projects approved by SLSC on 22.09.2010 under Stream – I comes to around Rs. 450.00, which will also be utilized during 2010-11.

Action Points:

- A dedicated RKVY Cell should be created in the Nodal Department at the State Headquarter headed by a Senior Official with necessary supporting manpower and infrastructure.

- Each Implementing Agency should nominate one Senior Officer as a link officer with the Nodal Department, who coordinates projects in the respective Agency and regularly liaise with the Nodal Department.

- Project Screening Committee headed by Secretary, Agriculture wherein all the Heads of Project Implementing Agency are the members to be created to scrutinize the proposals before putting upto SLSC for sanction.

- Allotting ID number to all projects and streamlining the reporting system to MoA to remove the present inconsistency in reporting and to comply with Rashtriya Krishi Vikas Yojana Database and Information Management System (RDIMS) on-line monitoring. The State Government should keep in touch with NIC at Delhi.

- The current status of all sanctioned projects (SSLC date-wise) from the beginning should be prepared on a separate statement along with respective ID number and giving the current status in the remarks column under one of these five categories viz., completed / modified and completed / on-going / modified and on-going / not executed to be de-sanctioned.

- The RKVY Cell would organize state level monthly meeting under the Chairmanship of Secretary, Agriculture to review the progress of RKVY projects.

- The Government of Goa may call for fresh tenders for the preparation of C-DAP and SAP, and should try to complete the process before March 2011.

s

Annexure-I

List of Participants in the  RKVY review meeting by NIRD Team at Panaji, Goa on 22.11.2010, chaired by Mr. Ganesh Koyu, IAS, Secretary Agriculture

| Sl.No. | Name of the Officer | Designation & Address |
| --- | --- | --- |
| 1. | Shr. Ganesh Koyu, IAS | Secretary (Agriculture), Secretariat, Porvorim-Goa |
| 2. | Dr. R.N. Hegde | Senior Fellow, NIRD, Hyderabad |
| 3. | Shri. S.S.P. Tendulkar | Director of Agriculture, Directorate of Agriculture, Tonca Caranzalem-Goa. |
| 4. | Shri. P. Tufani | Dy. Director of Agriculture, Directorate of Agriculture, Tonca Caranzalem- Goa. |
| 5. | Shri. Girish Kamat | Dy. Director of Agriculture, Director of Agriculture, Tonaca Caranzalem-Goa |
| 6. | Dr. H. Faleiro | Dy. Director, Department of Animal Husbandry & Veterinary Service, Panaji-Goa. |
| 7. | Dr. R.B. Dhuri | Manager, Goa State Milk Producers Union, Curti-Ponda |
| 8. | Dr. R.D. Naik | Veterinary Officer, Goa State Milk Producers Union, Curti-Ponda |
| 9. | Shri. Anil D Noronha | Zonal Agriculture Officer, Pernem |
| 10. | Shri. Audhut Sawant | Assitt, Agriculture Officer, ZAO Tiswadi |
| 11. | Smt. Frieda Barreto | Dy. Director of Agriculture, Director of Agriculture, Tonca Caranzalem-Goa. |
| 12. | Dr. Shamila Monteiro | Dy. Director, Fisheries, Department of Fisheries |
| 13. | Anjali M. Ticklo | Sr. Technician, Department of Fisheries |
| 14. | Tadeo Rodrigues | Asstt. Director, of Agriculture, Directorate of Agriculture, Tonca Caranzalem-Goa |
| 15. | Shri. Shivram Gaonkar | Zonal Agriculture Officer, Quepem |
| 16. | Joaquim D Souza | Zonal Agriculture Officer, Bardez |
| 17. | Shri. Sandeep Fal Dessai | Zonal Agriculture Officer, Salcete |
| 18. | Shri. SB. Dhaimodkar | Zonal Agriculture Officer, Ponda |
| 19. | Shri. Y.N Dessai | Asstt. Director of Agriculture, Directorate of Agriculture, Tonca Carazalem-Goa |
| 20. | Shri. Shrikant Mone | Agriculture Officer, Directorate of Agriculture, Tonca Caranzalem |

| Annexure- II Time lag in Sanction and Releases (Sector-wise – Project-wise) 2008-09 and 09-10 |
| --- |
| (Rs.`. in Lakhs) |
| Year | Sanction by DAC | Recipt at State | Release by State to Nodal Agencies | Release to PIA |
|  | Date | Amount | Date | Amount | Date | Amount | Date | Agency | Amount |
| 2007-08 | 23/11/07 | 50.00 | 17/01/08 | 50.00 |  |  |  |  |  |
|  | 3/1/2008 | 20.00 | 5/3/2008 | 20.00 |  |  |  |  |  |
|  | 28/03/08 | 100.00 | 21/4/08 | 100.00 |  |  |  |  |  |
| 2008-09 |  |  |  |  | 8/9/2008 | 57.65 | 18/09/08 | Directorate of Fisheries | 3.60 |
|  |  |  |  |  |  |  | 18/09/08 | Directorate of AHVS | 3.16 |
|  |  |  |  |  |  |  | 10/2/2009 | Goa State Milk Producers Union | 13.90 |
|  |  |  |  |  |  |  | 18/09/08 | Directorate of Agriculture | 36.99 |
| Total | 57.65 |  |  | 57.65 |
| Balance unutilised with Goa Dairy | -3.45 |  |  | -3.45 |
| Grand Total | 54.20 |  |  | 54.20 |
| 2009-10 |  |  |  |  | 19/11/09 | 16.58 | 4/12/2009 | Directorate of Fisheries | 1.01 |
|  |  |  |  |  |  |  | 4/12/2009 | Directorate of AHVS | 1.58 |
|  |  |  |  |  |  |  | 4/12/2009 23/02/10 | Goa State Milk Producers Union | 7.00 |
|  |  |  |  |  |  |  | 4/12/2009 | Directorate of Agriculture | 10.44 |
| Total | 16.58 |  |  | 20.03 |
| Balance unutilised of 08-09 with Goa Dairy | 3.45 |  |  | 0.00 |
| Grand Total | 20.03 |  |  | 20.03 |
| 2010-11 | 20/7/10 | 283.00 | 29/9/10 | 283.00 |  | 0.00 |  |  | 0.00 |

s