REPORT ON THE MONITORING OF RKVYIN KERALA AS AT 31ST January,2009

Dr. Geetha Kutty

Monitoring of the RKVY projects in Kerala was carried out during 16-19th February, 2009 in co-ordination with the office  of the  Director , PPM Cell , Kerala, (officer in charge of  RKVY in the state).   Separate discussions were held with the Agricultural Production Commissioner, Director of Agriculture, Director of Fisheries and Director of Research of Kerala Agricultural University (KAU) in addition to a review meeting of all the state level implementing officers of the various agencies involved in RKVY.  Selected innovative and best practice project sites of the department of agriculture, agricultural university and fisheries department were visited and meeting with various implementing agencies were also held in the districts of Thrissur, Kottayam and Pathanamthitta   .

1. General progress Status of  RKVY in Kerala ( 2007-08 and 2008-09)

(i)Total amount sanctioned under RKVY FOR  2007-08 was Rs.5501 lakhs, and the expenditure incurred as on 31.01.09 is  Rs.2786.68 lakhs (51%). Agency wise financial achievements under RKVY 2007-08 are furnished below.

Table 1.Sector-wise sanction/amount released/utilization of funds(2007-08)

| Sl.No | Department/Agency | Sanctioned amount (Rs.lakhs) | Expenditure (Rs.lakhs) | % Expenditure |
| --- | --- | --- | --- | --- |
| 1. | Department of Agriculture | 2190.90 | 1059.35 | 48 |
| 2. | Department of Animal Husbandry | 1551.50 | 598.50 | 39 |
| 3. | Dairy Development Department | 210.50 | 153.00 | 73 |
| 4. | KLDB | 148.50 | 148.50 | 100 |
| 5. | KSPDC | 145.00 | 145.00 | 100 |
| 6. | Fisheries Department | 91.50 | 91.50 | 100 |
| 7. | KAU | 465.00 | 382.33 | 82 |
| 8. | Soil Conservation | 10.25 | 10.00 | 98 |
| 9. | VFPCK | 160.50 | 121.17 | 75 |
| 10 | Horticorp | 3.50 | 1.20 | 34 |
| 11 | KAICO | 466.95 | 21.5 | 5 |
| 12 | Serifed | 56.85 | 54.63 | 96 |
|  | TOTAL | 5500.95 | 2786.68 | 51 |

An overall progress of  target  achievement (51%)  is reported  .

Agencies like KLDB, KSPDC, and  Fisheries Department have achieved cent percent  targets, and   agencies like  KAU, Serifed and Soil Conservation  are nearing completion . The Department of Animal Husbandry  , Horticorp, and KAICO are noted to be  still lagging  behind in their target achievement .  
(ii). RKY Projects of 2008-2009

Sector  wise allotment of projects is furnished in Table.2. Toal amount of Rs.6011 lakhs is allotted but fund release    to various agencies is getting initiated.

Table.2 Sector-wise sanction  of RKVY funds of 2008-09 in Kerala approved by the SLSC meeting held on 13-11-2008

| Sl.no | Agency | Sanctioned amount(Rs.inLakhs) | Remarks |
| --- | --- | --- | --- |
| 1. | Department of Agriculture | 2500.00 |  |
| 2. | Dept of Soil Conservation | 10.00 |  |
| 3. | Dpt of Minor Irrigation | 46.00 |  |
| 4. | KLDC | 58.21 |  |
| 5. | Dpt. Of Soil survey | 20.00 |  |
| 6. | VFPCK | 151.50 |  |
| 7. | Hoticorp | 50.00 |  |
| 8. | Dept of Animal Husbandry | 417.20 |  |
| 9. | Dairy Development | 212.47 |  |
| 10. | KFL | 400.00 |  |
| 11. | KLDB | 100.00 |  |
| 12. | KSPDC | 145.00 |  |
| 13. | MPI | 19.99 |  |
| 14. | Dept. of Fisheries | 411.40 |  |
| 15. | Dpt. Of Harbor Engineering | 200.00 |  |
| 16. | Matsyafed | 201.27 |  |
| 17. | ADAK | 275.00 |  |
| 18. | FIRMA | 22.00 |  |
| 19. | KAICO | 75.00 |  |
| 20. | Serifed | 42.70 |  |
| 21. | KAU | 462.92 |  |
| 22. | Dpt of C-operation | 100.00 |  |
|  | TOTAL | 6011.00 | Funds are being released only. Hence no expenditure is reported |

2. Physical and financial progress(2007-08)

2.1 Agriculture Sector

Forty eight percent financial achievement only is reported from this sector  in general in the state . The districts of Palakkad(14%) and Thrissur(40%) are lagging behind in implementation. The reasons reported for delay    are of seasonal nature and availability of machines as the projects are of Infrastructure   and farm mechanization related activities. The supply constraints, apparently, were not foreseen at the time of formulating the schemes.(Table  No. #- annexure 1)

Table.3 Physical and financial progress in agricultural sector

2.3 Animal Husbandry sector

The animal Husbandry sector in general( including, AH, Dairy,  KLDB, Poultry development )has achieved 90%  financial  achievement

2.3.1 Animal Husbandry

The  department of Animal Husbandry   has made  a financial achievement of 86 % and remarkable  outcomes are also reported

Table 4.  Physical and financial progress in Animal Husbandry Sector

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14

I Animal Husbandry 1 Calf feed susbsidy scheme Calf feed will be given at 50% subsidy which is limited to Rs. 6500/beneficiary, 500 calves of 4-6 months etc. will be enrolled under the scheme in Trivandrum, Kollam, Alappuzha, Pathanamthitta, Kottayam, Idukki, Ernakulam, Thrissur, Palakkad, Malappuram, Kozhikkod, Wayanad, Kannur and Kasargod districts 7000 0.065 455.00 455 100 2 Distribution of health care kits Health care kits will be given to 4000 dairy cows @ Rs. 400/kit. The kit comprises dewormers, vitamin, mineral supplements, ectoparasiticida, first aid medicines, disinfectants etc with 100% subsidy in Trivandrum, Kollam, Alappuzha, Idukki, Thrissur, Palakkad, Malappura, Kozhikkod and Wayanad districts; 3000 health care kits will be distributed with an assistance of Rs. 12 lakhs in Pathanamthitta district; 5000 health care kits will be given to dairy cows comprising dewormers, vitamin, mineral supplements, ectoparasticida, first aid medicines, disinfectants etc in Kottayam districts; Health care kits will be given to 2000 famale calves and 40000 dairy cows. kit comprises dewormers, vitamin, mineral supplements, ectoparasiticida, first aid medicines, disinfectants etc in Ernakulam district; Health care kits will be given to 2000 dairy cows comprising dewormers, vitamin, mineral supplements, ectoparasiticida, first aid medicines, disinfectants etc with 100% subsidy in Kannur and Kasargod districts 52000 0.004 208.00 0 0 3 Distribution of milking machine 4milking machines will be distributed to the departmental farms 4 0.5 2.00 0 0 4 Cattle insurance 2100 animals (cows & heifers) will be provided insurance for 3 years @ 6.6% with 75% subsidy in Trivandrum, Idukki and Kozhikkod districts; 2500 animals (cows & heifers) will be provided insurance for 3 years in Kollam districts; 2000 animals (cows & heifers) will be provided insurance for 3 years @ 6.6% with 75% subsidy in Pathanamthitta, Kottayam, Thrissur and Malappuram districts; 1200 animals (cows % heifers) will be provided insurance for 3 years in Ernakulam districts; 2500 animals (cows & heifers) will be provided insurance for 3 years at 75% subsidy in Kannur district 23679 143.50 23679 143.5 100 5 Cattle shed flooring Providing assistance for scientific construction of cattle shed floor with 100% subsidy to 500 beneficiaries who rear two cows in Trivandrum, Kollam, Alappuzha, Pathanamthitta, Kottayam, Idukki, Thrissur, Malappuram, Kozhikkod, Kannur and Kasargod districts; providing assistance for scientific construction of cattle shed floor with 100% subsidy to 200 beneficiaries who rear two cows in Ernakulam districts; providing assistance for scientific construction of cattle shed floor with 100% subsidy to 1000 beneficiaries who rear two cows in Palakkad district; providing assistance for scientific construction of cattle shed floor with 100% subsidy to 700 beneficiaries who rear two cows in Wayanad district. 6900 414.00 414 100 6 Buffalo rearing Promoting buffalo rearing by providing buffalos to 150 farmers in Kollam, Alappuzha and Kottayam districts; promoting buffalo rearing by providing buffalos to 5 farmers in Ernakulam district 505 101.00 101 100 7 Fodder cultivation Fodder cultivation 228.00 228 100 Total AH 1551.5 1341.5 86

2.3.2 Dairy Development

Cent percent  financial progress is reported and the implementation of the Automatic Milk Collection (AMCU) and the scheme is reported to be very useful and beneficial to the farmers.

Table 5.  Physical and financial progress in Dairy Development

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14

II Dairy Development 1 Strengthening of dairy cooperatives Establishment of Automatic Milk Collection Units which will give the accurate measurement of quality and quality of milk (cost of 1 AMC will come to Rs. 2.50 lakhs) in Trivandrum, Alappuzha, Pathanamthitta, Kottayam, Idukki, Thrissur, Palakkad, Malappuram, Kozhikkod, Kannur and Kasargod districts. Establishment of quality testing lab and supply of sufficient number of milk cans for strengthening the dairy cooperation in Ernakulam district 108 140.50 95 140.50 100 2 Quality control lab for milk – KLM I) Establishment of quality testing lab and strengthening the existing lab to cope up with the needs of additional equipments in Kollam districts. 1 10 10.00 0 10.00 100 3 Mobile clinic cum lab - PKD Ii) Providing modern equipments and testing facilities including mobile quality control to conduct vartious tests and to equip dairy cooperation in Palakkad district. 1 10.00 1 10.00 100 4 Quality testing labEKM Quality testing lab 1 14.00 1 14.00 100 5 Modernisation of dairy training centre- PKD Providing Model Dairy Farm Unit to promote organic Dairy Farm/Modernization of milk products section and lecture hall providing rain water harvesting system construction of ladies hostel and providing transport facility in Palakkad district. 1 10 10.00 1 10.00 100 6 Installation of solar water heater - WND Installation of power saving and eco friendly 10 solar water heaters with per unit cost of 0.7 lakh in Wayanad 10 0.7 5.25 5.25 100 7 Installation of can scrubbers -WND Installation of 10 Can Scrubbers with per unit cost of Rs.0 .5 lakh in Wayanad district. 10 0.5 3.75 3.75 100 8 Supply of SS Milking Pails WND Supplying 200 SS milking pails of 304 grade to dairy farmers in Wayanad district. 200 0.08 12.00 12.00 100 9 Establishment of Information Centre - KSD Development of 4 Dairy Extension service units having computer with all accessories and district. Development Office with modern multimedia computer system for Dairy Development activities in Kasargod 5 5.00 5.00 100 Total Dairy 210.5 210.5 100

Kerala Livestock Development Board

The Board has achieved cent percent financial progress and has brought  out remarkable  outcomes through the RKVY support (details  provided under production and productivity ) 
 Table 6.  Physical and financial progress in Kerala Livestock Development Board

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14

Kerala Livestock Development Board (KLDB) Providing free artificial insemination service to Milch animals Providing free artificial insemination senile to milch animals. Rs. 13.5 lakhs will be provided for the same in Trivandrum, Kollam, Alappuzha, Pathanamthitta, Kottayam, Idukki, Ernakulam, Thrissur, Malappuram, Kozhikkod, Kannur districts 148.50 148.5 100 Total KLDB 148.50 148.5 100

2.2.5. Kerala State Poultry Development Corporation (KSPDC) 
 Ninety per cent achievement of the project is reported with  best practices  like price control, popularization of artificial insemination  and cage system in broiler rearing.    
 Table 7.  Physical and financial progress in Kerala State Poultry Development Corporation

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14 Kerala State Poultry Development Corporation (KSPDC) Infrastructure development for the broiler breeding Infrastructure development for the broiler breeding farm at Kudappanakkunnu in Thiruvananthapuram district 145.00 145 100 Total KSPDC 145.00 145.0 100 Total AH sector 2055.50 1845.50 90

2.2.6. Fisheries

There are eight projects under the RKVY fisheries programme and cent percent achievement is a reported.  Best practices of integrated scampy farming in farmers field and alternate farming of prawn and rice also were reported.

Table 8.  Physical and financial progress in  Fisheries

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14 Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14 1 One Rice One Fish Programme Covering an area of approximately 11 ha of padasekharams for poly culture of scampi with crops in Alappuzha district 1.76 20.00 20.00 100 2 Introduction of fish seed in reservoirs Introduction of fish seed in reservoirs of the amount of Rs. 13 lakhs in Pathanamthitta district 13.00 13.00 100 3 Small major cart hatchery for the production of fresh water finger-lings Producing finger lings to fresh water ponds in order to maintain quality of fish lings in Pathanamthitta district 2.00 2.00 100 4 Assistance to traditional system of shrimp farming in filtration fields Bringing 17 ha of pokkali fields under improved shrimp farmin in Ernakulam district 9.00 11.36 9.00 100 5 To strengthen the activities of Uttanam Government Fish Seed Farm Strengthening the activities of Uttanam Government Fish Seed Farm at Parappanangadi in Malappuram district 10.00 10.00 100 6 Inland Fisheries Promotion To encourage the rearing and marketing of ornamental fishes, fresh water, prawn culture, crop rearing and group fish farming in Wayanad district. 50 0.25 12.50 12.50 100 7 Strengthening brackish water fishculture Strengthening of brackish water fishculture in Kottayam district 10.00 10.00 100 8 Strengthening of inland acqua culture and ornamental fish culture Strengthening of inland acqua culture and ornamental fish culture in Idukki district. 15.00 15.00 100 Total Fisheries 91.50 91.50 100

- KAU Projects

In general 82% financial achievement is reported. A number of innovative and best practices in research and technology popularization are being implemented.   Projects of farm mechanization, cashew apple production, banana seedling production and project on establishment of a gene sanctuary of fodder crops at Thumburmuzhy farm in Thrissur district were visited and encouraging outcomes were  noted. ( Table No.9-Annexure 2)

4. Other agriculture sector

4.1. Soil Conservation

Cent percent achievement of project implantation   is reported with predicted change in cropping pattern and crop production  
 
 Table 10.  Physical and financial progress   in Dept of Soil Conservation

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14 Soil Conservation Construction of pipe check dam Constructing a pipe check dam using RCC NPB Pipes to reduce the run off velocity and thus increase the water level in Thrissur district. 10.25 10.24 100 Total Soil consrvation 10.25 10.24 100

4.2.VFPCK

Seventy five percent financial achievement and remarkable physical outcomes in production are reported  
Table 11.  Physical and financial progress   in Dept of Soil Conservation

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14 VFPCK Strengthenning of farmers market Infrastructure support to farmers market 20 125.01 20.00 100.40 80 Supply of planting materials Establishment of hardenning unit etc. 10.00 4.80 48 Orghanic cultivation of vegetables Vermi compost units, homestead gardewn etc. 15.49 15.50 100 Plant health clinic Establishment of plant health clinic 10.00 0.47 5 Total VFPCK 160.50 121.17 75

4.3.Horticorp

Financial achievement of 34% is reported The RKVY programme of the Horticorp is on honey production promotion  through apiculture in homesteads. It is being  implemented in Thrissur District of Kerala.The Corporation has organized Beekeeping Orientation Training Programs to the selected beneficiaries before the supply of bee colonies and accessories.  The delay faced  in arranging bee colonies  and bee hives  is reported  as reason for low financial achievement .

Table 12.  Physical and financial progress   in Horticorp

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14 Horticorp Apiculture Apiculture in homesteads - 500 0.007 3.50 293 1.2 34 Total Hortcorp 3.50 1.20 34

4.4 KAICO

Only 44% of the target of financial achievement is noticed as still the machines are not made available from the firms .

Table 13.  Physical and financial progress   in KAICO

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14 Kerala Agro Industries Corporation (Kaico) Farm Mechanization a) Purchase of 20 numbers of combine harvesters - 20 19.5 390.00 206.46 53 b) Infrastructure facilitation for workshop. 1 34 34.00 0 c) Mobile workshop 1 12 12.00 0 d) Tools and machineries 1 18.6 18.60 0 e) Training and other unforeseen expenditure 1 12.35 12.35 0 Total Kaico 466.95 206.46 44

4.5. Serifed

Ninety six percent financial achievements are reported. Technology utilization for increase in productivity and profit is reported to be a best practices.

Table 13.  Physical and financial progress   in Serifed

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14

Serifed Distribution of Rotary Mountage Providing 800 rotary mountages equipment to improve the quality of cocoon in Alappuzha, Pathanamthitta, Malappuram, Kasargod districts 29.60 29.15 98 Training Organizing training programme to upgrade the knowledge of farmers in Pathanamthitta and Palakkad districts 1.50 0.80 53 Project to enhance the income of serculture farmers Providing necessary equipment like rotary montages, power sprayer, room heater, chowki plastic crate for improving the quantity and quality of cocoon in Thrissur district 6.80 20.76 305 Farm Mechanization Providing cultivator, harvesting machine and deflossing machine for farm mechanization in Palakkad district 8.30 2.59 31 Distrbution of Chawki Plastic Tray Providing 450 plastic crates to ensure proper hygiene 0.004 4.70 1.35 29 Seminar Conducting a seminar on the use of machinery in Alappuzha district 5.95 0 Total Serifed 56.85 54.64619 96

5. Status of District action Plan

It was reported that only one   district- Thrissur- has  finalised and submitted   district action plan  and all other 13 districts are in the process, and  yet to finalise and submit their plans. During  discussion with the  APC of Kerala, it was informed that to expedite the matter, a state level workshop of  all   the district level agencies concerned for  the C- DAPs  will be held during the first week of March 2009.

6. Monitoring arrangements under RKVY

Following the instruction of the Govt. of India, State level Monitoring Committee under the Chairmanship of the Agriculture production Commissioner was constituted on 11th October, 2008 to review the implementation of RKVY programme and to submit report to the state.  The Committee is expected to review on a monthly basis.  Principal secretary(Finance), Secretary(Agriculture), Secretary(Animal Husbandry), Secretary(Fisheries) Chief (Agri) of Planning Board, Director(Animal Husbandry), Director Fisheries, Director (Dairy Development),  Director (Agriculture) and Director(PPM Cell) are members of the committee. SLSC is actively involved in screening and selection     of the 2009-2010 RKVY projects.

7. Convergence   Practiced

Considerable degree of convergence was observed at various level and functions of   various projects of the RKVY projects of the state. Convergence of various nature -inter agency/ departmental, intersectoral, and intra agency could be identified as existing.

E.g.;  7.1 The paddy fallow land project  of  Pathanam Thitta block is an example of the convergence of agencies in the field .  Multiple agencies/departments irrigation, PRI, farmers Co operatives,   and other ongoing projects of the Department of Agriculture were utilsing the resources in the project activities

7.2. Fisheries department’s promotion of scampi production in farmers’ field through integrated farming   of technologies  is also an example of convergence

7.3. VFPCK has utilized the fund with other sources of funding to meet the agency’s goals - got Rs.8 lakhs from SHM for the rehabilitation of TC lab at Alathur : The RKVY fund for preparing the rehabilitated lab for the production of plantlets. In the case of marketing support by RKVY, the infrastructure facility was provided to those vipanies who have land or building, purchased/ constructed using VFPCK fund or GOK fund. This fund was provided by RKVY,GOK and VFPCK own fund. Other than this, SHM had provided fund for the specific projects namely, Banana, Vegetable and pineapple area expansion, Seed infrastructure development and rural market infrastructure development. Considering all the funds received by VFPCK 1.The share of RKVY is 15%; 2.The share of VFPCK is 10%; 3.Farmers share is 10%;The per ha investment of RKVY comes to Rs.314.7/-

7.4.      The project implemented for Women Empowerment in the Agriculture Scenario of Kannur District envisages empowerment of women in agriculture and allied sectors.  On and off farm interventions ranging from Rs. 3000 to Rs. 2 Lakhs have been approved for implementing the programme titled “Karshaka Sthree Sakthi Programme”.    The programme envisages gender dimension in all farm programmes,  foster community-centered systems,  provide nutrition security to women and child and make agricultural education gender sensitive.  The women folk in agriculture sector of the district are mobilized through group approach thereby bringing income generation by commencing agriculture and allied activities through small enterprises. Assistance for starting new enterprises for multifarious activities were extended and the project target of 500 enterprises was exceeded in a short span.  These enterprises   are  also example of convergence of sectors - Vegetable cultivation Banana cultivation, Tuber crops cultivation, Ginger cultivation, Turmeric cultivation, Medicinal plants cultivation Pineapple cultivation, Jasmine cultivation, Anthurium cultivation, Orchid cultivation, Coconut processing, Green house, Vermi compost, Mushroom cultivation, Bee keeping, Biogas and Animal Husbandr - Goat rearing, Poultry, Dairy, Quail rearing, Ornamental fisheries

8.  Gains in Productivity and Production after RKVY

8. 1.  Poultry sector: The RKVY support enabled supply of good quality COBB – 400 variety chicks at a lesser price than the market rate due to which farmers got the benefit of Rs.2.71 lakhs.Around 2.71 lakhs chicks have been distributed among farmers in Kerala and the price difference is Rs.1 per chick.  The net advantage is around Rs.2.71 lakhs. Quality and Scientifically processed meat made available to public at affordable price (10-20% less than market price).  Scientifically processed poultry meat is not available elsewhere in the State. Through RKVY project, KSPDC has become the chief agency in controlling the price of Broiler Meat in Trivandrum District. Support to 32 Integration Farms with a total capacity to rear 1.09 lakhs birds could also be provided.

8.2. Fisheries sector  :       By implementing the Project through RKVY Scheme, the production of Scampi, shrimp and fish  is found to be increased from 500-750 kg per hectare to 750-1000 kg per hectare, i.e., 20-25% of increase in production.  The average revenue is also increased to 20-25%.  About 20000 man-days were generated due to the implementation of the Scheme.  The additional fund/credit required for the farming was met by either Padasekhara Samithies or from Banks or Co-operative Societies, or in some cases, by the beneficiaries themselves.  By the implementation of the scheme in paddy fields, the paddy production is also increased to 15-20%. The preparation expense and feed cost is very less for fish farming under this Scheme. It is also noticed that the preparation expense of paddy field for cultivation is also came down due to the implementation of the scheme.   By rotating fish farming with paddy culture, the use of pesticides, insecticides, fertilizer, etc is minimum. Four farmers of RKVY scheme conducted organic scampi and paddy culture in 20 hectares in the Project area, also by utilizing the technical support from MPEDA  As a result, a better marketing system is evolved.

8.3. VFPCK: The support from RKVY was intended for the production of seedlings. As on date around 1 lakh seedlings of Brinjal, Chilly, Tomato ,Cabbage ,Cauliflower were produced and distributed. The seedlings are raised in the seedling trays supplied to the farmers under this scheme. Tissue culture lab will start functioning by march 20th 2009. The tissuie culture lab setup with RKVY funding has  target of producing  50000 plantlets of Manjeri Nendran variety of banana.The capacity of the plant is 30 lakhs plantlets and the production of the TC plants will be increased yearly assessing the demand of the TC plants every year. Field level managers of VFPCK will assess the demand in their area of operation. The demand will be consolidated at the district level and then the state level the yearly target will be arrived.

Improving the infrastructure facility of the farmer markets by providing temporary shed, computers, cash chest. Along with this price stabilization support as well as input marketing support and organic produce support.

These supports indirectly help to increase the sales turn over by 10-15% in the farmer markets which is  directly supporting around 15,000 farmers who are brining produces to these markets. The bargaining power of the farmers  increased and on an average the farmers are getting around Rs.3,000-Rs.5,000/season. More over the fair price support helps the farmers to tide over the price fall in the market.

8.4. Soil Conservation :       By implementing the Manjakunnu Pipe check dam project at Cheenikadavu, in Pananchery Panchayat of Thrissur district, an area of 510 hectare has been benefited and a net area of 150 hectare has been directly benefited by the construction of the check dam. It is expected that due to increased ground water recharge the agricultural production and productivity would be increased in the project area. Cultivation of vegetables, paddy and banana would be intensified in the project area by the implementation of the scheme. Another benefit perceived by implementation of the scheme is the ease with which the farmers can transport their products across the bridge constructed, which would save a considerable amount of money spent on transportation of agricultural produce.

8.5.Horticorp

The RKVY programme is implemented in Thrissur District of Kerala.The Corporation has organized Beekeeping Orientation Training Programs to the selected beneficiaries before the supply of bee colonies and accessories. Benefits of the programme were reported as- Crop productivity has been increased 15% to 20% in that area  through cross pollination by the honey bees;An average honey production of 10-15 kg/colony has been collected by the farmers.   Through the implementation of the scheme it is estimated that about 2930 Kg. of honey has been collected by them;The beneficiaries have received an additional financial benefits by selling the honey and bee wax produced by them;Created employment opportunities to the unemployed and young entrepreneurs.

8.6. KLD Board

The  KLD boarad has reported that milk production has  increased to 21.3 Lakh metric ton ,  compared to 20.6 lakh metric ton of the previous year.   It is also pointed out  that ,in the Artificial Insemination  centers of the inter - state boarder villages, spurious semen from unauthorized agencies at low price was used earlier. At present this tendency is reported as  reduced. Number of Straws used for consumption has reduced from 4 to 2.7. and as consumption rate of the animal has increased., the dry period per cow has shortened, leading to increase in the production and productivity per cow. Reduction in the inter calving period by one month of the existing cows results in an additional production of milk worth Rs.300 lakh per year.  So the better quality semen distributed through at low cost integrating Ksheeradhara project (Under NPCBB) and RKVY helped in increase production period productivity of milk. 17%increase in Artificial Insemination coverage and Increase in conception rate noticed. Inflow of low quality semen decreased .

Ksheeradhara  is a programme for  providing Free Artificial Insemination Services in Eleven Districts of the state.      Pure breed Semen of bulls like Jersey and HF are distributed through a selective breeding programme by enrolling cows which are having 12 litres or more production. Only one scheme on providing free artificial Insemination services in eleven districts of the state” with a total outlay of Rs.148.50 lakhs(Rs 13.5 lakhs per district) was sanctioned to KLDB under RKVY during 2007-08.The scheme is being implemented in eleven districts (excluding Kasargode,Wayanad and Palakkad where this facility is provided under the Special Livestock & Fisheries Package of the GOI) The funds were released during 2008-09 and the scheme was implemented w.e.f 01.05.2008 .Frozen semen doses worth Rs.148.50 lakhs have been distributed in the eleven districts of the state free of cost for impregnating the animals and the entire amount has been utilized.

8.7 Agriculture Sector

Departmental farms are functioning as the main production centres of quality planting materials.  Quality planting materials are vital and basic input for attaining higher yields.  For providing quality planting materials farms have to be provided with basic as well as sophisticated infrastructural facilities.  During 2007-08 under RKVY scheme an amount of Rs.152.75 lakhs provided for the infrastructural development of farm and the programmes are under implementation. In Kerala where paddy is the major cereal crop, the total quantity of seed produced for distribution during 2007-08 was 51945.30 quintals.  After the introduction of RKVY scheme the seed production has been increased to 59488.1 quintals during 2008-09 are as follows:-

| Year | Dept. of Agriculture | NSC (Qtls.) | KSSC (qtls.) | Total (Qtls) |
| --- | --- | --- | --- | --- |
| 2007-08 | 28626.30 | 18516.20 | 4802.80 | 51945.30 |
| 2008-09 | 40031.20 | 11013.60 | 8443.30 | 59488.10 |

The above figures shows that the share of Department in supplying the seeds has been increased after the introduction of the RKVY Programmes.

- Infrastructure Development .

From the PPM Cell it is reported that    In general about 45.74% of the total   fund allocation of rKVY  across the sectors  is   oriented towards  infrastructure  development  which will contribute  to long term  development in agricultural sector.

10.  Innovative Projects under RKVY in Kerala

10. 1.KAU Project on Field testing, Training and Service Centre for Agro Machinery .

This  project is  implemented from the Agricultural Research Station , KAU, Mannuthy, Thrissur  is aimed to build up a treasury of agro machinery suitable to  Kerala.  The project activities  are  targeted (a) to provide training  on operation, maintenance and servicing of agro machinery and implements in order to  create skilled manpower resource in the state( b)  to provide a central facility for the farmers of Kerala to  meet agricultural demands by providing access to machinery and their service  and maintenance and (c) to provide a facility for development and testing of agro machinery for the state agricultural scenario. The project team   together with stakeholders  including farmers  has identified  and enlisted   a set of agro machinery suitable for promoting   mechanization in the farming sector of Kerala  such as-  paddy transplanter, power reaper, thresher cum winnower, power tiller, power weeder, Electric bush cutter, electric hedge trimmer, power saw, rotovator, ridger, mould board plough, disc plough, mobile copra drier, sit and climb coconut climber, double cone cono weeder, triple piston pump, helical blade puddler and hand tools like felling  knives, sickles, mattocks, crow bars, spades, trash collectors, fruit harvesters, wheel barrows etc . The above listed machinery have been procured as  a part of the project for training the farmers. These are also being hired out to farmers at nominal rates through the farm machinery facilitation centre set up  under the project.

Innovative training programmes are initatiated and imparted from the project   As part of these trainings in the use of different agro machinery have been conducted at the station and at various field locations after the commencement of the project. Demonstrations in outside the state like Andhra Pradesh and  for participants  from Andaman  and Nicobar Islands are also  conducted . A one year long stipendary training programme on operations, maintenance and servicing of agro machinery  has also commenced with five trainees and another batch of ten members is proposed to  start soon. A mobile training unit has also been established to provide on site training in different agro machinery at farmers fields as per their need and demand. These trainings are being carried out with a wider vision of developing a highly trained group of Agro Machinery Operations Service Executives(AMOSE) in the state-  who will be trained in the repair, aftercare, and maintenance of all agro machinery and the trained participants will be awarded  with certificate. It is envisioned to prepare and deploy one lakh AMOSE in the state within three years.

As part of providing access to machinery and their service and maintenance  to farmers, the project has successfully established a farm machinery facilitation centre at the  project site which provides the farmers with repair and maintenance services of all kinds of agro machinery. This  centre has also stocked authentic spare parts of various agro machinery to help the farmers obtain genuine spares at reasonable price.

without delay, and thereby carry out their agricultural operations on time. The stock of spares at this unit is very helpful and farmers have already purchased spares  worth Rs.0.35 lakhs.  A Mobile Agro Machinery Repair and Service Unit (MAMRSU) has also been established to provide mobile and on-site repair and maintenance facilities to the farmers.

The project has also been instrumental in the setting up of Agro Machinery Centres  at Panchayath level. People  who have completed training from the station have been encouraged with all technical  support to register  themselves as Self Help groups of Agro machinery Service Centres(AMSC)  with the aim of providing farmers with timely and trained agro machinery operations at Panchayth level so as to overcome problems of scarcity of labour. Seven such AMSCs are already registered in Thrissur district and are actively engaged in mechanized  agricultural operations on contract basis. They are being continuously rendered all technical support in terms of machinery and skill development programmes by the project. Thy are also involved and participating  in the  mobile training programmes of the station. From among these self help groups ,nine members   took part in  demonstration of mechanical paddy transplanting in seven districts of Andhra Pradesh.

The project is also providing facility for development and testing of agro machinery for the state agricultural scenario, by carrying out field testing and trials of agro machinery  after levying  fees . As part of this service ,KAU has been approached by M/s Reddlands Ashlyn Plc, Coimbatore to test three models of combine harvesters and one model of mechanical transplanter manufactured by them.

10.2    KAU Project of  Establishment of a gene sanctuary of fodder crops at Thumburmuzhy in Thrissur district.

The project taken up from the Kerala Agricultural University  to establish a gene sanctuary of fodder crops   has turned out to be  an innovative one. This is established in Thumburmozhy farm of the   KAU.   As part of the project   a germ plasma collection  of  various fodder  crops in south India  is developed . The collection includes breeder varieties as well as  farmer identified   fodder  crops.  Testing of the varieties suitable to the region is taken up and   large scale production of fodder  is also started by installing innovative water conservation using plastic layering in tanks  and irrigation facilities in the farm . Infrastructure is established for  fodder processing like silage   and biogas production.  Now the farm is largely depending on biogas for its energy needs.   Fodder demonstration units and training courses  on fodder cultivation and fodder banks  to the nearby  villages are also on anvil from this project. A new variety of fodder – Thumburmozhy  is also getting evolved as part of the project . Utilsiing the close proximity of the farm to the famous tourist spot of Athirapallly dam , there is high scope of connecting the project  with eco-tourism also.

10.3. Automatic Pricing Milk Pricing Machine

The Dairy Development Department  as part of the RKVY funding,  has taken up   Establishment of Automatic Milk Collection Units(AMCU) in dairy cooperatives.  Collection, measuring and testing of milk from framers using this device  is reported to be a best as well as innovative practice.   In the conventional set up ,  the  dairy co-operatives were following manual measurement and testing of the fat content  for price fixing which in was contributing lot of biases and loss on the part of the farmers. The AMCU is found to be very accurate and fix each  lot of milk supplied by  farmer then and there  without any manipulation.  It helps to ensure the accurate measurement of quality and quality of milk  and is  found to contribute an increase of benefit  by  about Rs1 to 1.15 to the farmers.  Through RKVY,  the system is installed in selected dairy co-operatives in  Trivandrum, Alappuzha, Pathanamthitta, Kottayam, Idukki, Thrissur, Palakkad, Malappuram, Kozhikkod, Kannur and Kasargod districts .

10.3 Change in Cropping Pattern in Pathanamthitta  by re introducing  Rice Cultivation

Pathanamthitta is district of  a true tropical diversity adorned with fertile agricultural land, plantations and forest.  Paddy, Rubber, tapioca, vegetables, Rubber, Banana, Pepper, tuber crops etc. are extensively cultivated. Seventy (70) % of the total area is used for rubber cultivation and only 3% of the land is used for paddy cultivation as per the latest Statistics.  Moreover, there is considerable reduction in area under paddy cultivation due to conversion and other reasons.  The area under rubber cultivation increases day by day due to favourable market conditions whereas paddy cultivation decreases due to lack of proper irrigation water in the required time, non-availability of labour, high wage rate, high cost of cultivation, absentee land ownership especially by NRIS etc. The size of farm holdings in the district is very small restricting economic operation, since 88% of the farmers holding size is below one Ha.

Major issues

The task before the planners in the district is to arrest the tendency of paddy land conversion, increase the area of paddy cultivation, reduce the problem of labour shortages, convert the small and uneconomic holdings into operational economic holdings through group farming and optimal use of available water resource etc. During 1997-98 paddy was cultivated in 8267 Ha. Which is reduced to 3051 Ha. During 2007-08.  A progressive reduction in area of cultivation under paddy may be due to high cost of cultivation, non-availability of labour especially at the time of harvesting season, lack of sufficient high yielding varieties of seeds for the district, lack of suitable machines of the district, increased pest diseases, lack of availability of water at required time and required quantity and lack of marketing arrangement for procurement of crop at the time of harvest.

Critical Gap/Bottle Neck faced  in converting the large tract of  rice  fallows  as cultivable  were

- Shortage of Agricultural labours especially during harvesting period.

- Lack of  irrigation canals .

- Leakages and sweepages of existing canals coupled with inefficient management of irrigation system.

- Scattered wet lands on each Panchayat.

- Uneconomic operational holdings.

- Absentee land ownership.

- Lack of procurement and assured market price during the harvest.

- Farming has become a supplementary occupation to majority .

- Lack of integrated approach/practice in agriculture and allied sector.

- Lack of backward and forward linkages.

- Absence of insurance in farm sector to ensure protection against natural calamities like wind, flood etc.

- Low productivity.

- Lack of organic farming.

- Absence of processing units. And

- Lack of  marketing facility and procuring

As part of  RKVY project , specific infrastructure development works in Pandalam Thekkekara, Thonnellur and Thumpamon was taken up to  reintroduce rice cultivation . Mavara Puncha and Karingalichal puncha in Pandalam Block having an area of 900 ha. Is the most important paddy area in Pathanamthitta district which had been left mostly as follow land for years long.  To increase the paddy production in this district, it was very necessary to improve the infrastructural facilities in Pandalam block.  The scheme implemented successfully with the help of farmer group and self help groups.  The main aim of the scheme is to assist the padasekhara samithies to provide adequate infrastructural facilities.  The project proposes to   bring minimum of 147.00 ha. fallow land under paddy cultivation and improvement of existing infrastructural facilities. Irrigationa canals are revived and soil mining from the field is arrested.    Already 167.00 ha. fallow land  is brought under cultivation through crop seasons . In the last season  procurement of rice through farmers co-operatives was arranged with aremunerative price of Rs. 10.75/kg The project is  expected to increase rice production  wit a produce of  835 MT paddy worth Rs.91.85 lakhs. 
 
 11. Best Practices

11.1   The State Poultry Development Corporation (KSPDC)  was setting certain good practices   through the RKVY project  funding   .

  - Supplied good quality COBB – 400 variety chicks at a lesser price than the market rate due to which farmers got the benefit of Rs.2.71 lakhs.

  - Around 2.71 lakhs chicks have been distributed among farmers in Kerala and the price difference is Rs.1 per chick.  The net advantage is around Rs.2.71 lakhs.

  - The existing farmers are more motivated and have taken up this venture due to the availability of good quality chicks, an important input in broiler farming.

  - The drainage to the state exchequer by way of import of poultry meat is estimated as Rs.700/- Crores.  This drainage has been checked to some extend as the total value of meat produced so far was around Rs.4 crores.

  - Augmentation of internal production of meat and a boost to Food Security o the state.

  - Quality and Scientifically processed meat made available to public at affordable price (10-20% less than market price).  Scientifically processed poultry meat is not available elsewhere in the State.

  - Rs.9 lakhs has been paid to farmers as rearing charges under broiler integration.

  - In poultry meat sector, Corporation could control the price of meat in local market by effective market intervention. When the price of live broiler birds in the local market was Rs.80/- per kg.  Corporation could sell the birds at Rs.61/- per kg. that too including 12.5% VAT.   The processed meat was also sold at a very lesser price. Corporation could sell the meat and the live broiler birds at 10-15% below the market rate and this resulted in sudden dip in market price to Rs.61/-.

  - This is the first time in the history of the Corporation that such a market intervention was made possible.  This is rather an ever thought impossible mission made possible. This sector was ignored by all saying that we can’t compete with outside agencies as the cost of production is always higher in our state.  The broiler farmers in the state were begging at the mercy of the outside players, for their survival.

  - The age old concept that we can’t anything in broiler market was broken by us with the help of farmers in the state.  We give inputs to them and they rear, we will take back it process it and supply to consumers.  The farmers get  rearing charge of Rs.6-7/- bird and the consumers get good quality meat (with out harmful residues) at lesser price.

This is  reported as beneficial to farmers as a farmer rearing 5000 birds would get Rs.30000-35000/- month as rearing charge that too with out any risk involved.  The recurring expenditure to rear 5000 birds is around 5 lakhs and farmers need not bother about it.  Even if they invest this much amount farmers can never expect a profit to the tune of this amount owing to the reason that there is always volatile price variations in the market.  These farmers are approaching KSPDC in integrate them in broiler production.  So this will be a boon to hundreds of farmers in the state as for each kilo for broiler meat produced and consumed in the state, a farmer is getting Rs.6/-.  Considering that our internal consumption of poultry meat is around one lakh tones, the benefit to the farmers can be un-imaginable.

This is beneficial to the consumers as well  as the meat has the following advantages:-

- The meat is free from any harmful residues like growth promoters;

- Since De-skinned the cholesterol level is reduced to the minimum;

- The meat is soft, tender and juicy since ageing is completed;

- The meat is highly hygienic and with good quality;

- The price is lesser than the market rate (10-15% including VAT).  Local vendors are selling the live bird and price charged is for the live weight.  (Including the blood and skin).  In this context our meat is again priced less by another 10%.

The State is also benefited from the outcome

- As the drainage of this amount will make our economy more vibrant;

- Creates employment opportunities;

- Supply of safe and quality meat protects the health of the public;

- More tax increase state’s revenue;

- Helps to strengthen the state food security programme;

- Quality meat supplied at reasonable price to the public is part of government intervention in commodity market. Through RKVY project, KSPDC has become the chief agency in controlling the price of Broiler Meat in Trivandrum District.

- Support to 32 Integration Farms with a total capacity to rear 1.09 lakhs birds.

| Market Rate |  | KEPCO Rate |
| --- | --- | --- |
| Rate of Live Broiler Chicken | Rs.74/- (without tax) |  | 1 kg. KEPCO Broiler Meat | Rs.88.88/- (without tax) |
| Maximum meat generated from Live Broiler Chicken (without skin) | 650 gm. |  | Including tax | Rs.100.00 |
| So the rate for 1 kg. meat | Rs.114/- (without tax) |  | Price variation between KEPCO Meat & Other Market rate | Rs.25.12/- (without tax) |
| By purchasing 1 kg. of KEPCO meat public can save Rs.25.12 (without tax) |

11.2. Project oru nellum oru meenum(onerice , one fish farming ) implemented in alappuzha district,during

Agency for Development of Aquaculture, Kerala (ADAK, ) is functioning under the administrative control of State Fisheries Department, and was  established in the year 1989.  The prime objective of the Agency is to promote the overall aquaculture development in the State.  Now, the Agency is mainly engaged in the promotion of various types of Inland and Brackish water aquaculture on fish, prawn, scampi, mussel, oyster, crab, integrated paddy-cum-fish culture, etc.    The Kuttanadu Region of Kerala is a highly complex Eco system.  It is the deltaic formation of four major rivers, namely, Meenachil, Pampa, Manimala and Achancovil together with the low lying areas in and around the Vembanad Lake.  It is water logged area almost throughout the year and lies below the mean sea level.  It consists of 54 Revenue Villages spread over ten Taluks in Alappuzha, Kottayam and Pathanamthitta Districts, with a geographical area of 54935 Ha.

Paddy is the main crop in Kuttanad.  Kuttanad is known as the rice bowl of Kerala.  Paddy is generally cultivated in two main seasons, namely, Puncha (November to March) and an additional crop known as virippu from June to October.  In Kuttanad, two crop of paddy cultivation is conducting an approximate area in 10000 Ha only.  In 30000 Ha, there is only one crop paddy, i.e., for about 4 to 5 months only.  The remaining 7 to 8 months, the Padasekharams are idling without any crop.  The farmers are utilizing these idling time for the cultivation of fish and prawn by Oru Nellum Oru Meenum Programme, for increasing their income by reducing the cost in paddy cultivation. In the saline belt of Alappuzha District, particularly Cherthala Taluk, paddy/shrimp farming is practiced  in Pokkali and chetty virippu paddy fields.  About 2000 hectares of paddy fields are utilized  for paddy and shrimp farming.  Paddy culture is practiced during monsoon season and shrimp farming from November to March.

ADAK implemented Oru Nellum Oru Meenum Scheme in the paddy fields and polders of Kuttanad Region of Alappuzha, Kottayam and Pathanamthitta Districts from 2002 to 2006 in 1515 hectares with the financial support of the State Government.  The average production of scampi and fish was 500 to 750 kg per hectare.  Even though there are great potential areas for fish and scampi farming in Kuttanad, due to the lack of sufficient fund in the State budget for the subsequent years, the scheme was not taken up further.  But it could be initaiated and continued  during the year 2007-2008, as part of the   RKVY through State Fisheries Department.

Project activities of ORU NELLUM ORU MEENUM (SCAMPI/SHRIMP/FISH CULTURE).

An area of 60.70 hectare was  brought under Scampi/fish culture and an area of 153.96 hectare was  brought under shrimp culture with the financial support of RKVY.       In the Kuttanad region of Alappuzha district, 60.70 hectares  were brought under the culture of scampi and fish.  12.66 lakhs numbers of scampi seeds and 0.7235 lakhs numbers of fish seeds stocked during February-March’2008.  After a period of 8 to 9 months, the farms were harvested and 27.27 tones of scampi and 27.568 tones of fish for a Revenue of Rs.60.2183 lakhs were obtained.  The scheme was implemented in ten padasekharams of Kuttanad and it was benefited to 104 farmers.

In addition to the above scheme, the RKVY support has  helped the shrimp culture area, i.e, the saline region of Alappuzha district (Pokkali Region- Cherthala Taluk) an area of 153.96 hectare was  also brought under shrimp culture.  76.85 lakhs numbers of shrimp seeds were stocked during October-December’2007.  After a period of 4-5 months of culture, the farms were harvested and 90.824 tones of shrimp for a revenue of Rs.1.9405 crore were obtained.  The Scheme was implemented in 42 farms in Pokkali Region and it was benefited to 53 farmers.

BENEFITS

By implementing the Project through RKVY Scheme, the production of Scampi, shrimp and fish found to be increased from 500-750 kg per hectare to 750-1000 kg per hectare, i.e., 20-25% of increase in production.  The average revenue is also increased to 20-25%.  About 20000 man-days were generated due to the implementation of the Scheme.  The additional fund/credit required for the farming was met by either Padasekhara Samithies or from Banks or Co-operative Societies, or in some cases, by the beneficiaries themselves.  By the implementation of the scheme in paddy fields, the paddy production is also increased to 15-20%. The preparation expense and feed cost is very less for fish farming under this Scheme. It is also noticed that the preparation expense of paddy field for cultivation is also came down due to the implementation of the scheme.   By rotating fish farming with paddy culture, the use of pesticides, insecticides, fertilizer, etc is minimum. Our four farmers of RKVY scheme conducted organic scampi and paddy culture in 20 hectares in the Project area, also by utilizing the technical support from MPEDA  As a result, a better marketing system is evolved.

12. Staus of  Agriculture Machineries in Kerala

KAICO agency has reported that Government of Kerala has sanctioned and released an amount of Rs.466.95 Lakhs for carrying out of mechanization activities under Rashtriya Krishi Vikas Yojana Scheme 2007-08.  The Government has directed the Corporation to procure Combine Harvester for the amount thus sanctioned. Accordingly Purchase Order was issued for the supply of 18 Nos. of Combine Harvesters and supply is being effected and the same will be completed before 31st of March, 2009.

The total requirement of Combine Harvesters is around 280 Nos. in the state. The RKVY contribution is around 7% of the total requirement. As the allotment cover a small percentage of the total requirement, request to sanction additional fund for meeting the further demand of Combine Harvesters in the State.  Kerala is facing acute scarcity of farm labourers moreover mechanization is must in Kerala to improve the efficiency of Corporation there by enhancing the productivity. Considering above we have already evolved project of setting up of Agro Engineering Service Centers/Custom Hiring Centers for Agro Machineries. Following machineries are selected to maintain adequate level of quality and economy for the purpose of providing the same to the farmers in the most potential areas. - .Rice Transplanter (8 row, mat type,),Rice Combine Harvester, Power Tiller with trailer ,60 HP Tractor with front end loader and back hoe (5.),5 HP Tractor with tipping trailer ,High Discharge Pump set ,Mini Tiller, Rotovator  and Power Reaper. A major portion of the farmers in the state are  with  farm  size    below one acre. Procuring of these machineries for cultivation will be difficult for such farmers because of the high investment involved individually. Therefore KAIC intends to achieve following objectives by implementing this scheme. (-Hiring out modern agricultural machinery to farmers on rental basis. andTo provide timely repair and service for all machineries by utilizing the service from the regional workshops of KAIC.) Total financial outlay of Rs. 798.75 lakhs is estimated to commission this project in  following districts-Thiruvananthapuram ,Kollam, Allapuzha, Ernakulam, Malappuram ,Wayanadu, Pathanamthitta ,Kottayam,Trissur ,Palakkad

KAIC is already implementing a package for Setting up Custom Hiring Centers for Combine Harvesters at Pathanamthitta, Kottayam, Trissur, and Palakkad.  These Centers will be augmented with other machineries to function as full fledged Agro Engineering Service Centers.

Annexure - I

Table.3 Physical and financial progress in agricultural sector

2 Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % 3 Component Qty Rate Amt 4 1 2 7 8 9 10 13 14 5 I Agriculture 6 Thiruvananthapuram 7 1 Management of coconut yellowing disorder Giving assistance as subsidy for affected palms in Thiruvananthapuram district ,000 palms 21.176 0.85 18.00 18.87 18.00 100 8 2 Management of coconut yellowing disorder Additional assistance (Actual cost Rs750 Amount given at present Rs 250 + Rs 500 per palm) for cuting and removal of 5000 Nos of old and senile, diseased and unproductive palms 5000 0.005 25.00 5000.00 25.00 25 9 3 Providing Irrigation facilities and renovation of irrigation/drainage canals (Paddy) Irrigation facilities in Keezhmagom padasekaram 18.00 0.00 0 10 4 Providing Irrigation facilities and renovation of irrigation/drainage canals (Paddy) Renovation of irrigation/ drainage canals in Varkala 16 10.00 3.44 34 11 5 Promotion of small scale agro processing and value addition ventures Establishment of 20 worksheds and to provide 85% assistance for starting new value addition units by SHGs in Thiruvananthapuram district 2 2.5 5.00 5.00 100 12 6 Revival and revitalization of deplt farms DAF - Development of TC lab and starting of vermi compost units 20.00 8.67 43 13 7 Homestead Farming Vegetable cultivation programme - Rs 15000per ha for Haritha Sangams, Kudumbasree and other SHGs in 1000 ha 100 0.15 15.00 15.00 100 14 Total 111.00 75.11 68 15 Kollam 16 1 Revival and revitalization of deptl farms DAF - Development of TC lab and starting of vermi compost units 21.65 21.65 100 17 2 Revival and revitalization of deptl farms SSF - Repair of bunds, purchase of garden tillers and inputs 6.25 6.25 100 18 3 Revival and revitalization of deptl farms Coconut Nursaries - Iririgation facilities 2.00 2.00 100 19 4 Sustainable development of rice Repair of bund, desiltatioon of canals etc. 102.00 17.20 17 20 5 Sustainable development of rice Inputs for taking up paddy cultivation 5.00 1.90 38 21 6 Homestead Farming Vegetable cultivation programme - Rs 15000per ha for Haritha Sangams, Kudumbasree and other SHGs in 1000 ha 100 0.15 15.00 13.80 92 22 7 Modernisation and strengthening of information centre Modernisation and strengthening of information centre 3.75 3.71 99 23 8 Revival and revitalization of deptl farms Cashew farm Kottarakkara 10.00 6.67 67 24 Total 165.65 73.18 44 25 Pathanamthitta 26 1 Revival and revitalization of deptl farms SSF Pullad -Repair of bunds, purchase of garden tillers and inputs 25.00 8.01 32 27 2 Revival and revitalization of deptl farms Sugarcane farm, Panthalam 15.00 0 28 3 Sustainable development of rice Rendering 578.3 ha of rice fallows cultivable in 33 padasekarams in 14 pancharyaths 113.00 113.00 100 29 4 Sustainable development of rice Improvement of drainage -69.25, Installation of 2HP pumpset -1.25, Farm machinary-1.5, Engin thara- 5, Repair of breached Bunds 3 lakhs (Changed) 80.00 21.28 27 30 Total 233.00 142.29 61 31 Alappuzha 32 1 Sustainable development of rice Infrastructure development for padasekarams in Alappuzha 7 48.00 7.00 37.21 78 33 2 Sustainable development of rice Cost of paddy seed supplied under natural calamity (MT) 41.821 6.00 41.821 6.00 100 34 3 Sustainable development of rice Specific infrasrtucture work in padasekarams Karingali and Peruvachal 4 140.00 68.33 49 35 4 Sustainable development of rice Assistance for crop loss compensation during flood 2007 (No of farmers) 38606 147.00 38606 147.00 100 36 Total 341.00 258.54 76 37 Kottayam 38 1 Farm Mechanization Petty and para 6 2.25 13.50 6 13.49 100 39 2 Coconut Development programme Distribution of rocker sprayers (Coconut) 50 0.03 1.50 52.00 1.51 101 40 3 Coconut Development programme Installation of pumpsets - 500 Nos @ Rs. 6000/ (coconut) 500 0.06 30.00 528.00 30.00 100 41 4 Homestead Farming Plant protection equipments for vegetable cultivation 500 0.01 5.00 511.00 5.00 100 42 5 Homestead Farming Portable pumpsets for vegetable cultivation 100 0.1 10.00 100.00 10.00 100 43 Total 60.00 60.00 100 44 Ernakulam 45 1 Development of Marketing Infrastructure Market infrastructure 5.00 0.00 0 46 2 Coconut Development programme Planting materiels 4.00 4.00 100 47 3 Coconut Development programme IPM 1.00 1.00 100 48 4 Construction of biogas plant Community Biogas 3 Nos @ Rs. 3.5 la 3 3.5 10.50 0.00 0 49 5 Construction of biogas plant Solid waste recycling plant/gober gas plant - 100 Nos @ Rs. 12000 100 0.12 12.00 12.00 100 50 Total 32.50 17.00 52 51 Idukki 52 1 Banana Cultivation Programme Cultivation of banana in an additional area of 600 ha in Idukki district; 600 0.15 90.00 600.00 80.00 89 53 2 Cocoa Development Programme Rehabilitation of 297 ha of land; Hybrid seedlings for rejuvenation programme for cocoa in Adimaly, Kattappana, Nedumkandom and Idukki blocks 50 0.15 7.50 50.00 7.00 93 54 3 Homestead Farming Vegetable cultivation programme -for Haritha Sangams, Kudumbasree and other SHGs 1000 0.15 150.00 580 117.17 78 55 Total 247.50 204.17 82 56 Thrissur 57 1 Revival and revitalization of deptl farms Production of planting materiels - 7 farms @ Rs. 25000 1.75 1.75 100 58 2 Homestead Farming Vegetable cultivation programme - for Haritha Sangams, Kudumbasree and other SHGs 100 0.15 15.00 50.00 15.00 100 59 3 Repair of damaged bunds Repair of damaged bunds 150.00 50.00 33 60 Total 166.75 66.75 40 61 Palakkad 62 1 Farm Mechanization Digital moisture metre - 11 0.2 2.20 0 0.00 0 63 2 Farm Mechanization Automatic seed processing machine 1 10 10.00 0 0.00 0 64 3 Farm Mechanization Machanised seed treatment drum @ Rs.50000/ 5 0.5 2.50 0 0.00 0 65 4 Revival and revitalization of deplt farms SSF-Alathur - Harvesting and other machinary - Transporting machin 8.00 0 0.00 0 66 5 Revival and revitalization of deplt farms SSF-Kongad - Irrigation tank, waiting shed, fencing etc 6.40 0 0.00 0 67 6 Revival and revitalization of deplt farms SSF-Muthalamada - Machanisation, Drip irrigation etc 7.00 0.00 0 68 7 Revival and revitalization of deplt farms SSFAnanganady - Mushroom production unit & repair work 5.65 0.00 0 69 8 Revival and revitalization of deplt farms SSFKunnanur - Borewell, Green house 6.00 0.00 0 70 9 Revival and revitalization of deplt farms Central Orchard, Pattambi - Farm road and automatic weather station 12.00 0.00 0 71 10 Revival and revitalization of deplt farms HDF - fencing & weed cutter 2.80 0.00 0 72 11 Revival and revitalization of deplt farms ISDF - Chain link fencing 15.00 0.00 0 73 12 Revival and revitalization of deplt farms O& V Farm - overall development 11.95 0.00 0 74 13 Sustainable development of rice Seed production incentives to farmers - tone 870 0.03 26.10 17.90 69 75 14 Sustainable development of rice Assistance for stocking seed in the localised godowns- tone 3480 0.0025 8.70 0.60 7 76 15 Development of soil health management system Pump house (Rs 57500/) and lamina flow chamber in the soil testing lab, Pattambi 4.10 0.00 0 77 Total 128.40 18.50 14 78 Malappuram 79 1 Cut and removal of diseased coconut palms Cut and removal of bud root affected coconut palms 1000 0.005 5.00 1000.00 5.00 100 80 2 Sustainable development of rice Kole land development Seed distributin- mt 4.90 35.00 4.90 100 81 3 Coconut Development programme Copra drier 20 0.075 1.50 2.00 0.00 0 82 4 Coconut Development programme Micro Irrigation (coconut)-ha 25 0.5 12.50 23.61 8.50 68 83 Total 23.9 18.40 77 84 Kozhicode 85 1 Cut and removal of diseased coconut palms Cut and removal of bud rot affected coconut palms 34000 0.005 170.25 34000 167.80 99 86 2 Sustainable development of rice Addl area Puncha 50.00 0 87 3 Banana Cultivation Programme Promotion of organic banana cultivation in 80 ha @ Rs. 20/plant in Kozhikkod district - ha 40 0.5 20.00 38.00 11.85 59 88 4 Cut and removal of yellow leaf disease affected arecanut palms Cut and removal 12500 arecanut trees at the proposed rate of Rs. 400/tree in the Kunnamangam, Koduvally, Kunnaummal Perambra of Balussery district in Kozhikkod district 20000 0.0025 50.00 17500 19.15 38 89 Total 290.25 198.80 68 90 Wayanad 91 1 Development of Marketing Infrastructure Farmers market through Kudumbasree - 7 units @ Rs. 50000/ 7 5 35.00 7.00 35.00 100 92 2 Agro input promotion programme Enhancement in the supply of quality inputs like planting materials, biocontrol agents at fair price; setting up of 5 units for the production of biomanuals and biocontrol agents in Wayanad district 5 6 30.00 0.00 0 93 3 Food security programme Setting up of 500 units for the production of seeds/seedlings by Tribal SHGs per unit cost will be 0.005 lakhs in Wayanad 500 0.005 2.50 0.75 30 94 4 Establishment of solar light traps Establishment of 50 solar tight trap units in major rice growing areas within a period of one year. Per unit cost is 0.2 lakh in Wayanad district 25 0.2 5.00 0.00 0 95 5 Floriculture Promotion Helping small farmers in the procurement of planting materials and infrastructure support for establishing 100 production units consisting 500 plants, shade net to irrigation facilities etc in Wayanad district. 10 0.8 8.00 0.40 5 96 6 Setting up and strengthening of eco shops Setting up of 10 ecoshops units to establish market outlet for organic, ethnic and value added products. Reference for mobile units in Wayanad district 5 2.5 12.50 0.00 0 97 7 Construction of biogas plant 50 biogas plants with a minimum capacity of 2m3 will be constructed for the production of enriched bio-manure. 50 0.075 3.75 2.31 62 98 8 Development of soil health management system One unit of soil health management system will be established for the collection of soil samples and analyses for micro and macro nutrients, pH etc in Wayanad district 10.00 0.00 0 99 9 Farm Mechanization Establishment of farm machinery centre -Unit 10 5 50.00 9.00 45.00 90 100 Total 156.75 83.46 53 101 Kannur 102 1 Revival and revitalization of deplt farms Infrastructural development of five departmental farms in Kannur district (Karimbam, Kommeri, Kankol , Vengad, , Palayad -) @ Rs 5 la per farm 25.00 0.00 0 103 2 Cluster based coconut estates Implementation of coconut based farming system in a compact area basis through group management system 12 50.00 39.37 79 104 3 Women empowerment in the agricultural scenario Assistance in starting new women enterprises by starting 500 bioproduction unit consisting mush room spawn unit, vermi compost unit VAM etc in Kannur district 100 100.00 514.00 85.46 85 105 4 Mango processing unit Providing Rs. 5 lakh as margin money for availing institutional finance for product diversification in mango district. 5 1 5.00 0.00 0 106 Total 180.00 124.83 69 107 Kasargod 108 1 Distribution of coconut seedlings Coconut seedlings '000 nos 20 0.25 5.00 20 5.00 100 109 2 Homestead Farming Coconut, intercropping with tubers and vegetable @ Rs. 15000/ha in 328 ha 20000 49.20 0.00 0 110 Total 54.20 5.00 9 111 Total for Agriculture 2190.90 1346.03 61

Annexure – II

Table 9.  Physical and financial progress  of kAU projects

Sl No Project Name Physical Targets Fin target (Rs lakhs) Physical Progress Financial Progress % Component Qty Rate Amt 1 2 7 8 9 10 13 14 Kerala Agricultural University (KAU) Establishment of bio control lab Establishment of a biocontrol laboratory for crop. Pest management at Vellayani in Trivandrum district. 50.00 40.43 81 Setting up of spawn production and commercial mushroom cultivation Setting up spawn production and commercial mushroom cultivation at the instructional farm, Vellayani in Trivandrum. 20.00 16.15 81 Establishment of Research Centre for organic farming and sustainable agriculture Establishment of research centre for organic farming and sustainable agriculture at Vellayani in Trivandrum. 8.00 7.95 99 Establishing polyclonal progeny orchard for jack and mango Establishment of polyclonal progeny orchard of jack and mango at Vellayani in Trivandrum district. 15.00 13.80 92 Hybrid coconut seedlings production unit Setting up hybrid coconut seedlings production unit at Balaramapuram in Trivandrum district. 20.00 12.17 61 Establishment of planting material production unit Establishment of a planting material production unit at Farming System Research Station, Sadanandapuram in Kollam district. 3.00 2.96 99 establishment of a goat unit Establishment of a goat unit at Farming System Research Station, Sadanandapuram in Kollam district 3.00 2.85 95 Comprehensive coconut care programme for root wilt affected area Launching a comprehensive coconut care programme for root wilt affected areat at Onattukara in Alappuzha district 20.00 15.40 77 Strengthening of rice cultivation Strengthening of rice cultivation in Onattukara (RARS, Kayamkulam) in Alapuzha district. 7.00 6.66 95 Establishment of Sugarcane Processing Unit Establishment of a sugarcane processing unit at Sugarcane Research Station, Thiruvalla in Pathanamthitta district. 10.00 6.13 61 Establishment of Centre for biowaste recycling Establishing centre for biowaste recycling at Kumarakom in Kottayam district 15.00 9.77 65 Establishment of a Protocol for organic cultivation of cardamom Setting up a protocol for organic Cardamom production at Cardamom Research Station, Pampadumpara in Idukki district. 15.00 9.40 63 Developing protocol for organic rice production Development of protocol for organic rice production in Pokkali tracts, RRS Vyttila in Ernakulam district. 25.00 23.88 96 Hatching Unit for brackish water fisher Setting up a Hatchery unit for brackish water fishes at Puthuvypu in Ernakulam district. 20.00 19.42 97 Establishment of a acqua clinic Establishment of an acquaclinic at Panangad College of Fisheries in Ernakulam district 15.00 14.85 99 Strengthening of analytical lab for quality testing & certification of produce of 20 medicinal plant 25 nos Strengthening of analytical lab for quality testing & certification of produce of medicinal plants at Aromatic & Medicinal Plants Research Station, Odakkali in Ernakulam district. 22.00 18.39 84 Establishment of a progeny orchard for mass production of banana suckers Establishing a progeny orchard for mass production of banana suckers at Banana Research Station, Kannara in Thrissur district 20.00 17.74 89 Field testing, training and service centre for agro machinery Setting up field testing, training and service centre for agro machinery at Munnuthy in Thrissur district. 25.00 23.44 94 Cashew apple processing unit Setting up a Cashew apple processing unit at Madakkathara in Thrissur district. 22.00 15.93 72 Processing and product development in fruit crops Establishing processing of and product development in fruit crops at Vellanikkara in Thrissur district 15.00 14.67 98 Setting up of Vermi compost production unit Setting up a Vermi Compost production unit at Vellanikkara in Thrissur district. 10.00 3.12 31 Establishment of a gene sanctuary of fodder crops Establishment of a gene sanctuary of fodder crops at Thumburmuzhy in Thrissur district. 20.00 20.00 100 Establishment of polyclonal progency orchard of cashew Setting up a polyclonal progeny orchard of cashew at Cashew Research Station, Anakkayam in Malappuram district. 20.00 19.01 95 Strengthening of soil testing lab Strengthen soil testing lab of KVK, Ambalavayal in Wayanad district 20.00 14.11 71 Establishment of Rural Bio Resource Complex Establishing a Rural Bio Resource Complex at Ambalavayal in Wayanad district. 15.00 11.44 76 Establishment of a Protocol for organic cultivation of pepper Establishing a Protocol for organic pepper production at Pepper Research Station, Panniyur in Kannur district. 10.00 8.12 81 Studies on genetic improvement of desert mangoes of Malabar region Undertaking a study on the genetic improvement of desert mangoes of Malabar region is proposed at Regional Agriculture Research Station, Pilicode in Kasargod district. 10.00 8.06 81 Research to develop hybrid coconut suited to Kerala. Undertaking project to develop hybrid coconut suited to Kerala at the Regional Agriculture Research Station, Pilicode in Kasargod district. 10.00 6.50 65 Total KAU 465 382.32942 82