Uttar Pradesh

Monitoring Report of RKVY for Uttar Pradesh

(As at 28, February 2009)

Prof. R.P. Singh

Background

Rashtriya Krishi Vikas Yojna (RKVY) was launched in the state with the main objective of ensuring a holistic development of agriculture and allied sectors. It was expected by the state to initiate specific projects with clear objectives for agriculture and allied sector under two streams (At least 75% of the allocated amount shall be proposed under stream-I for specific projects while the amount under stream-II will be available for strengthening the existing state sector schemes and filling the resource gaps) within definite specified period. In the State Agriculture Plan, major areas have been identified to increase the productivity and profitability of farming system major project focuses on:

- Preparing District Agriculture Plans based on Agro climatic conditions, availability of technology and natural resources;

- Ensuring consideration of local crops/priorities/needs;

- Providing flexibility to the Districts in the process of Planning and executing Agriculture and allied Sector Scheme;

- Reducing the yield gaps in the important crops through focused interventions;

- Maximizing returns to the farmers in Agriculture and allied sectors;

- Bringing quantifiable changes in the production and productivity of various components of Agriculture and allied sectors; and

- Encouraging public investment in Agriculture and allied sectors.

Various programmes to be implemented under this Yojana (RKVY) in the state for various major sectors are:

- AGRICULTURE

- Soil Health: Improvement of Soil and Fertilizer Testing Laboratories, Organic Farming Systems, Green Manuring and Soil Health card Programmes.

- Water Resources & Management:  Underground Pipeline System, Micro-irrigation and Ridge and Furrow System of Paddy Cultivation.

- Seed Production and Seed Replacement Rate: Production & Supply of Seeds, Seed Production at Government Farms and Seed Treatment Unit at Gram Panchayat level.

- Technology Dissemination: Customized Farmers Training & Extension and on-line Agriculture Monitoring through Application of ICT, Integrated Farmers Training Centre and Farmers Study Tour and placement of subject matter specialists at Nyay Panchayat Level for dissemination of technology.

- Farm Mechanization: Establishment of Farm Mechanization Centre at Panchayat level.

- HORTICULTURE SECTOR

  - Small and Marginal Farmers and Women Empowerment:  Protected Cultivation in Low Tunnels of vegetables, Healthy Nursery Raising of Vegetable Crops, Nutritional Kitchen Gardens.

  - Entrepreneur Development: Vegetable Production, Floriculture, Backyard Mushroom Units, Hi-tech Green House.

  - Arid and Rainfed Farming: Improvement of Cultivation of Seed Spices in Arid Region.

  - Commercial Fruit Production:  Rejuvenation of Mango and Guava orchards and High Density Planting of Mango and Guava.

  - Sericulture: Incentives for Mulberry plantation and Establishment of New Tissue and Food Testing Laboratories at state level.

- ANIMAL HUSBANDRY: Year round Fodder Production, Strengthening of Artificial Insemination Centres, and Disease Surveillance & Quick Alert System.

- DAIRY DEVELOPMENT: Hygienic Milk Production, Commercial Dairy Farming Unit, Mini Milk Processing Units, Dairy Training Workshop for Women and Bulk Milk Collection Units.

- DEVELOPMENT OF FISHERIES: Demonstration & Training of Fish Culture, Renovation of Village Ponds and Development of New Hatcheries.

- POULTRY DEVELOPMENT: Incentives for small poultry units.

In addition, it was expected to have convergence of various ongoing activities. It was also proposed that besides enhancing productivity and profitability of the farm sector risk( which is not still covered)should also be emphasized at the State Level for implementation of such scheme. It was expected that implementation of these schemes will substantially enhance the growth rate in agriculture sector by more than 4 percent.

Administrative arrangements for RKVY

Additional Director (Extension) has been nominated as Nodal Officer for the Planning and Implementation of RKVY by the Principal Secretary Agriculture. He is assisted by one Dy. Director, one Accountant and one Office Assistant with computer knowledge. At the district level, Agricultural Technology Management Agency (ATMA) is the coordinating agency for the implementation of RKVY.  ATMA has already been constituted in all the 71 districts of the State.

Status

The monitoring visit of the State was taken up during March 09-11, 2009. Three meetings were held with Dr Mukesh Gautam, the Additional Director (Agricultural Extension) and also Project in-charge of the RKVY along with the Sri E.A. Ahmad, consultant responsible of the overall functioning of the RKVY in the state of Uttar Pradesh. During discussion with the senior level officials at the state level it was reported that a meeting was held last month at the state level and funds were allocated to various departments. However, details of the activities for which funds were allocated were not available. Sri E.A. Ahmad had requested several times all the departments to provide progress and details of activities planned and implemented by them in different districts. However, such details were not available at the headquarters and he assured us that he will requested all the department concerned again to provide the details of various activities planned and taken up in different districts by concerned departments. Till the date of the report such information was not provided by the state to the monitoring team

The monitoring team had a meeting with the Additional Director (Extension), who is the State Level Nodal Officer for Planning and Implementation of RKVY and other officers in the department besides a  meeting with Agricultural Finance Corporation,  the consultants for preparation of State Agriculture Plan and District Agriculture Plans for 66 districts.

It was observed that:

- Based on approved DAPs, State Action Plan (SAP) has been prepared and approved by the S.L.S.C.

- All District Agriculture Plan (DAPs) of 71 Districts have been duly approved by respective District Planning Committee (DPC) and Agriculture Technology Management Agency (ATMA).

- Up to 28th February, 2009, the Government of India had released Rs. 103.90 crores for the year 2007-08.  Further it released Rs. 158.29 crores for 2008-09. Against these releases the State Government has sanctioned Rs. 296.52 crores under the project to various departments.  The total expenditure till 28th February, 2009 was Rs. 218.54 crores.

- The Sector/Scheme/Component wise Physical and Financial progress under the scheme has been provided.

- Convergence has been proposed between RKVY and various central and states’ ongoing schemes for e.g. NAREGA etc.

- Since the implementation of the scheme, no study on ratio of seed replacement/requirement has so far been conducted.

- All the Departments are providing special attention to naxal infested areas and has fixed special targets/facilities for the same. However, no specific scheme under RKVY for naxal areas has been proposed separately.

- Three meetings of S.L.S.C. for approval of the projects and to monitor the progress under the scheme were held on 3rd March 2008, 17th October 2008 and 3rd March 2009. The proceedings of all the meetings were circulated to all the members.

The Sector/Scheme/Component wise Physical and Financial progress under the scheme for the year 2008-09 is given in Table 1. Since, implementation of the RKVY Scheme is in its first year, the effect of the scheme on productivity and production is yet to be seen but it is expected to have significant impact.

Table 1:

Physical & Financial Progress under – RKVY in Uttar Pradesh (upto 28 February, 2009)

| Sl. No. | Scheme | Financial in Lac Rs. | Physical | Remark |
| --- | --- | --- | --- | --- |
|  |  | Avail. Amt. | Utilised Amount | Component | Unit | Target | Achievement |  |
|  | AGRICULTURE |  |  |  |  |  |  |  |
| 1 | Strengthening of soil testing labs | 600.00 | 227.39 | Construction of new labs. | No. | 20 | Work in progress |  |
|  |  |  |  | Repair of labs. | No. | 30 | Work in progress |  |
|  |  |  |  | Purchase of chemicals for testing | - | - | - | Purchase order has been placed. |
| 2 | Land improvement in ravenous areas (Katri) of Ramganga | 100.00 | 98.70 | Reclamation of degraded soils | Ha | 700 | 505 | - |
|  | NAFED |  |  |  |  |  |  |  |
| 1 | Certification of organic Agriculture Management Systems | 2067.00 | 213.41 | Supply of soil culture | No. | 137801 | 82680 |  |
|  |  |  |  | Demonstrations | No. | 3160 | 391 |  |
|  |  |  |  | Experts visits, ICS documentation and Data uploading | No. | 6389 | 6335 | Continuous process |
|  | Agricultural Finance Corporation (A.F.C.) |  |  |  |  |  |  |  |
| 1 | Customized farmers Training & Extension | 1202.00 | 56.47 | Customized training and demonstrations of farmers | No. | 2423 | 2423 |  |

| Sl. No. | Scheme | Financial in Lac Rs. | Physical | Remark |
| --- | --- | --- | --- | --- |
|  |  | Avail. Amt. | Utilised amount | Component | Unit | Target | Achievement |  |
|  | U.P. BEEJ VIKAS NIGAM |  |  |  |  |  |  |  |
| 1 | Establishment & Strengthening of seed processing plant | 500.00 | 500.00 | Supply of machines and its installation | No. | 11 |  | Tenders are invited, completion by 15th March, 2009 |
|  | Horticulture and Food Processing |  |  |  |  |  |  |  |
| 1 | Strengthening of seed farm, training centre, exposure visit, T&V programme, fencing of new orchard | 400 | 2.48 | Seminar-cum-gosthi/exhibition |  |  |  |  |
|  |  |  |  | District Label | No. | 71 | 62 |  |
|  |  |  |  | Division label | No. | 18 | 16 |  |
|  |  |  |  | State label | No. | 6 | 1 |  |
|  | Animal Husbandry |  |  |  |  |  |  |  |
| 1 | Strengthening of Deep Frozen Semen Production Centre, Training & Extension | 399.99 | 365.13 | Production of foundation seed | Qtl | 17000 | - |  |
|  |  |  |  | Training and Extension of Pashu-palak | No. | 82000 | 77200 |  |

| Sl. No. | Scheme | Financial in Lac Rs. | Physical | Remark |
| --- | --- | --- | --- | --- |
|  |  | Avail. Amt. | Utilised Amount | Component | Unit | Target | Achievement |  |
|  | Fisheries |  |  |  |  |  |  |  |
| 1 | Area Extension for fisheries Development | 400 | 60 | Establishment of hatcheries | No. | 2 | - | Work in progress |
|  |  |  |  | Establishment of training Centre | No. | 1 | - | Money transferred to Nirman Nigam |
|  |  |  |  | Data base & E-governance of Water resources | No. | 39 | - | Money transferred to concerned officer. No. of District 39 |
|  |  |  |  | Conservation of natural fish Resource in river |  |  |  | Work in progress |
|  |  |  |  | Operational expense on training centre |  |  |  | Money allotted to concerned officer |
|  |  |  |  | Inter State training of fish keepers | No. | 40 | 40 |  |
|  | Minor Irrigation |  |  |  |  |  |  |  |
| 1 | Energization of 29075 tube wells of Department | 10409 | 10409 | Energization of tube wells | No. | 24858 | 12836 |  |

| Sl. No. | Scheme | Financial in Lac Rs. | Physical | Remark |
| --- | --- | --- | --- | --- |
|  |  | Avail. Amt. | Utilised amount | Component | Unit | Target | Achievement |  |
|  | Agriculture University, Faizabad |
| 1 | Seed Production Program by University | 363.4 | 363.4 | Seed Production | - | Renovation of Irrigation channels, seed godowns and threshing floor | Finalized | Advance money drawn in favour of working agency |
|  |  |  |  | Farm Implement | - | Purchase of New and advance equipment | Order placed to UP Agro |  |
|  |  |  |  | Tube wells Constructions | No. | 10 | Work in progress |  |
|  |  |  |  | I.P.M. |  | Purchase of equipments | Order placed |  |
|  |  |  |  | Soil amelioration |  | To ameliorate the ill soils of the seed production farms | Tender has been invited | Procurement will be made within financial year |
|  |  |  |  | Training on safe seed storage and seed production | No. | 16 | 13 |  |

| Sl. No. | Scheme | Financial in Lac Rs. | Physical | Remark |
| --- | --- | --- | --- | --- |
|  |  | Avail. Amt. | Utilised amount | Component | Unit | Target | Achievement |  |
|  | Agriculture University, Kanpur |
| 1 | Seed Production Program by University | 602 | 602 | Strengthening of farms | No. | - | - | Tenders have been invited Targets will be achieved by March, 2009 |
|  | P.C.D.F. / Dairy |  |  |  |  |  |  |  |
| 1 | Saghan Mini Dairy Yojana | 1201.87 | 1201.87 | Establishment of Mini Dairy (Beneficiary selection) | No. | 11150 | 965 |  |
| 2 | Vehicle tracking system | 74.97 | 74.97 |  |  |  |  |  |
|  | U.P.DASP |  |  |  |  |  |  |  |
|  | Development activities | 7000 | 7000 | ICTD demonstrations | No. | 101462 | 72610 |  |
|  |  |  |  | Field days | No. | 1768 | 1246 |  |
|  |  |  |  | IPM demonstrations | No. | 884 | 476 |  |
|  |  |  |  | Soil health cards and | No. | 60000 | 60000 |  |
|  |  |  |  | Activities of other sectors |  |  |  |  |
|  | Contingency | 729.2 | 473.39 |  |  |  |  |  |
|  | Total | 26049.43 | 21648.21 |  |  |  |  |  |

General Observations

Additional Director (Agricultural Extension) has been given the additional responsibility for the proper implementation of RKVY as Nodal Officer at the state level supported by a consultant. But, at the state level information relating to various activities/schemes being implemented by different department is not available. During discussion with the consultant it was observed that allocation of funds to various departments have been made in SLSC but detailed information on the district where activity/scheme has been started/implemented and how much funds have been actually spent on such schemes in each district by each department is not available. Apparently, the monitoring format given by DAC is not followed and the agencies are not familiar. He has requested several times for such details but till the time of writing the report it was not made available. It seems that the office at the state level is not adequately staffed to handle such problem. This scheme does not seem to have priority over other schemes as Additional Director (Agricultural Extension) has been given several responsibilities such as Food Security Mission and agricultural extension, etc. Time constraints and dedicated staff  devoted for such important scheme has not received adequate attention. The convergence of schemes has not been properly understood even at the state level. In fact, it is not possible to assess the impact of this project at the field level due to lack of relevant information to verify. Moreover, field visit at this stage might not provide any fruitful result.

The project team at the State level seems to be very weak. This needs to be strengthened. The projects already commissioned did not show convergence of programmes/ projects.  However, it is hoped that the new projects based on DAP will have the convergence. Arrangement for internal monitoring of the projects under RKVY seems to be very weak. There is a need to constitute an effective internal monitoring cell at the State level. It was also mentioned during the discussion that the person responsible for the project has no information about the earlier monitoring reports to take necessary action for improving the implementation of the project and making mid term corrections.

It is important that the implementing authority (Nodal Office) at the state level as well as district level to have proper data base as specified in the monitoring formats provided by DAC so that the monitoring team can select the district more systematically for visit. It is also suggested that the SLSC should take up review of the implementation, initially, with a focus both on process and progress monitoring. Progress monitoring of financial allocation of funds to various departments, as per specified formats, is necessary to check if projects /schemes/activities are based on the needs of the farmers and to facilitate effective convergence of services and funds.